## M Hipp ere.109
GULBARGA ELECTRICITY SUPPLY COMPANY LIMITED
Name of the Work :shifting of consumers Meters from inside to outside the premises of LT installation and replacement of existing electromechanical energy meters by static meters in Gulbarga District under DDUGJY on Total Turnkey basis
Name of the Contractor: M/s Vishwanath Projects Limited, House No 3-5-874/A, Flat No 401 4th Floor, Hyderguda, Hyderabad (telangana)
LOI No & Date : GESCOM/CEE(O)/SEE(Technical) AEE(DDUGJY)18-19/62017-30 dt 2-02-2019
DWA No & Date : GESCOM/CEE(O)/SEE(Technical)/AEE(DDUGJY)/INDENT-1037/DWA/2019-20/10023-32 dated 10-05-2019 for Supply and erection portion.
5th bill ERECTION PORTION | [11 empty] | Annexure-I
Invoice No/Bill No:VPL/GLB/MeterShifting/ Erection/109/19-20 dt: 08.03.2020 | [11 empty] | WORK ORDER NO : DK-33566 Dt: 16.03.2019
S.No | Item Description | UOM | HSN CODE | Total Qty | Ex-works Price | GST in Rs | Total amount (Including GST) | Previous Bill caimed Qty | Claimed Qty | Cumulative Qty(Including This Bill) | unit ex works price | ex works price (total) | GST (18%) in Rs | GST Amount In Rs. | Total Value
1 | 2 | 3 |  | 4 | 5a | 5b | 5c=5a=5b | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
ERECTION PORTION :
1 | Deep Drawn Metal Meter Box along with suitable screws for fixing to the wall. | Nos. | 85371000 | 118777 | 11072391.94 | 1993078.06 | 13065470 | 1930 | 113 | 2043 | 93.22 | 10533.86 | 16.78 | 1896.14 | 12430
2 | Realeasing and refixing of meter | Nos. | 39174000 | 118777 | 17816550 | 3206979 | 21023529 | 1930 | 113 | 2043 | 150 | 16950 | 27 | 3051 | 20001
3 | Fixing heavy gauge PVC Pipes using inverted wood plugs in case of RCC ceiling and RCC wall stone structure of raw plugs in case of brick walls and cement palstering damaged portion using heavy gauge saddles at an interval of 700 mm using NF screws (2/1) | Nos. | 85444999 | 118777 | 27882900.75 | 5018328.25 | 32901229 | 1930 | 113 | 2043 | 234.75 | 26526.75 | 42.25 | 4774.25 | 31301
Total | [7 empty] | 10: 54010.61; 12: 9721.39; 13: 63732
less 10 % amount payable after completion | [7 empty] | 13: 5401.061
NOW Claiming 90% on Ex works price | [7 empty] | 13: 48609.549
100% Taxes | [7 empty] | 13: 9721.39
Total amount of Invoice | [7 empty] | 13: 58330.939
Total Amount in words Fifty eight thousand three hundred and thirty one rupees only
CERTIFICATE
Certified that the above materials have been supplied by the M/s Vishwanath Projects limited , as shown as per DWA. The same have been stored at GULBARGA
site and using for shifting of consumers Meters from inside to outside the premises of LT installation In Aland Sub-division , Gulbarga Rual Division Under DDUGJY on Total Turnkey Basis.
Certified that the quantitty of materials furnished in the bill verified and these material found as per Gescom specifications.
Certified that we have physically verified the above materials
| Section Officer | [5 empty] | Asst Executive Engineer(Ele) | 10: Executive Engineer (Ele)
| O&M Section | [5 empty] | O&M Sub Division | 10: O&M Rural Dn.No.1
| Madan Hipparga | [5 empty] | Aland | 10: KALABURAGI.

## M Hipp ere.109(A)
TAX INVOICE
ERECTION BILL
Name of the Work: shifting of consumers Meters from inside to outside the premises of LT installation and replacement of existing electromechanical energy meters by static meters in Gulbarga District under DDUGJY on Total Turnkey basis Name of the Contractor: M/s Vishwanath Projects Limited, House No 3-5-874/A, Flat No 401 4th Floor, Hyderguda, Hyderabad (telangana) LOI No & Date: GESCOM/CEE(O)/SEE(Technical) AEE(DDUGJY)/2018-19/62017-30 dt 2-02-2019 DWA No & Date: GESCOM/CEE(O)/SEE(Technical)/AEE(DDUGJY)/INDENT-1037/DWA/2019-20/10023-32 dated 10-05-2019 for Supply and erection portion
5th BILL ERECTION PORTION |  |  |  |  | Annexure-I
WORK ORDER NO : DK-33566 Dt: 16.03.2019
INVOICE : VPL/GESCOM/GLB/Meter Shifting/Erection/109/19-20 dt 08-03-2020
Address : Vishwanath Projects Ltd, Hounse No. 1-1495/G/87, C/o. Dr.K.T.Paladi, Goudutai Nagar, Kalaburigi - 585102 |  |  | TEL | 040 - 23211660
|  |  | FAX | 040 - 23210198
|  |  | TIN No | 29370771492
|  |  | CST No | 29370771492
|  |  | GSTIN No | 29AACCV2054N1ZY
To: The Executive Engineer,(O&M) GESCOM. GULBARGA RURAL1 Division, |  |  | Invoice No | VPL/GLB/METER SHIFTING/109/19-20
|  |  | Invoice Date | 08.03.2020
|  |  | Cust.DWA No | GESCOM /CEE(O)/SEE (Technical)/AEE (DDUGJY)/Indent-1037/DWA/2019-20/shifting of Meter (Gulabarga).
|  |  | Cust.DWA Date | 10.05.2019
|  |  | L.R No & Date | Attached
Bank Details: Vishwanath Projects Ltd., Bank Name: ICICI Bank, A/CNO:000851000149 Branch: Khairatabad,hyderabad, IFSC CODE: ICIC0000008 |  |  | Transporter | Attached
Customer Code
|  |  | Customer GSTIN No | 29AABCG8895R1ZD
Customer CST No
Customer TIN No
Sl.No | Particulers |  |  |  | Amount Rs.
1 | Separate Annexure Enclosed of the Station Materials |  |  |  | 54010.61
2 | Freight and Insurance
|  | I) Total Amount Before Tax |  |  | 54010.61
|  | a) Add : CGST |  |  | 4860.695
|  | b) Add : SGST |  |  | 4860.695
c) Add : IGST
|  | II) Tax Amount : GST (a+b+c) |  |  | 9721.39
|  | Now Claiming 90% Ex-works ans Total Gst 100% |  |  | 58330.939
Total Amount in words Fifty eight thousand three hundred and thirty one rupees only |  |  | TERMS OF PAYMENT
|  |  | Retention 10% Amount after Completion |  | 5401.061
|  |  | Net Payable Amount |  | 58331
For Vishwanath Projects Ltd.
Authorised Signatory
1. W.O .N O & Date : DK-33566 dt :16-03-2019
2. Estimate Cost : Erection Cost : Rs. 63732 /-
3. Name of the Authority : Executive Engineer( Elect), O&M Division-I, GESCOM, Gulbarga.
4.Name of the Agency : M/S Vishwanath Projects Limited, Hyderabad.
5. Date Of Commencement : 10.05.2019 |  |  |  | 6. Date Of Completion : 26.12.2019
7. Date Of Measurment : 18.01.2020 |  |  | 8. MB Book No. |  | Page no
1.DI Date : GESCOM /CEE(O)/SEE(Tech)/EEE(DDUGJY)/19-20/13566-81/dt :28-05-2019
2. BG NO: 2423-BG-22-2019 dt .02-03-2019 to 25/11/2020
Certificate:
Certified that the above materials have been supplied by the TTK contractor of M/S Vishwanth Projects Limited.,
As shown as per DWA, the same have been stored at Kalaburagi,Tq and District Kalaburagi .
site and using for shifting of consumers Meters from inside to outside the premises of LT installation
in Aland Sub-Division, Gulbarga Rural Divisional ,Gulbarga District under DDUGJY on Total Turnkey basis
Certified that the quantitty of materials furnished in the bill verified with supporting invoices and these materials found as per Gescom specifications.Certified that we have Physically Verified the above materials
| Section Officer |  | Asst Executive Engineer(Ele) |  | Executive Engineer (Ele)
| O&M Section |  | O&M Sub Division |  | O&M Rural Dn.No.1
| Madan Hipparga |  | Aland |  | KALABURAGI.

## M Hipp retn.109
GULBARGA ELECTRICITY SUPPLY COMPANY LIMITED
Name of the Work :shifting of consumers Meters from inside to outside the premises of LT installation and replacement of existing electromechanical energy meters by static meters in Gulbarga District under DDUGJY on Total Turnkey basis
Name of the Contractor: M/s Vishwanath Projects Limited, House No 3-5-874/A, Flat No 401 4th Floor, Hyderguda, Hyderabad (telangana)
LOI No & Date : GESCOM/CEE(O)/SEE(Technical) AEE(DDUGJY)18-19/62017-30 dt 2-02-2019
DWA No & Date : GESCOM/CEE(O)/SEE(Technical)/AEE(DDUGJY)/INDENT-1037/DWA/2019-20/10023-32 dated 10-05-2019 for Supply and erection portion.
5th RETENTION BILL | [9 empty] | Annexure-I
Invoice No/Bill No:VPL/GLB/Meter Shifting/ Retn/109/19-20 dt: 08.03.2020 | [9 empty] | WORK ORDER NO : DK-33566 Dt: 16.03.2019
S.No | Item Description | UOM | HSN CODE | Total Qty | Ex-works Price | GST in Rs | Total amount (Including GST) | Previous Bill caimed Qty | Claimed Qty | Cumulative Qty(Including This Bill) | unit ex works price | ex works price (total) | GST (18%) in Rs | Total Value
1 | 2 | 3 |  | 4 | 5a | 5b | 5c=5a=5b | 6 | 7 | 8 | 9 | 10 | 11 | 12
SUPPLY PORTION :
1 | Supply of Deep Drawn Metal Box | Nos. | 85371000 | 118777 | 55361959.7 | 9965390.3 | 65327350 | 1930 | 113 | 2043 | 466.1 | 52669.3 | 0 | 52669.3
2 | Supply of Heavy gauge PVC conduit pipe 25mm dia 2mm thick. | Mtr | 39174000 | 1187770 | 21641169.4 | 3895885.6 | 25537055 | 19300 | 1130 | 20430 | 18.22 | 20588.6 | 0 | 20588.6
3 | Supply wiring for lighting/power circuit using one of PVC insulated 1.1 kv class standed Aluminium 6 sqmm single core | Mtr | 85444999 | 2375540 | 22140032.8 | 3990907.2 | 26130940 | 38600 | 2260 | 40860 | 9.32 | 21063.2 | 0 | 21063.2
Total | [7 empty] | 10: 94321.1; 12: 94321.1
Total Supply Value | [7 empty] | 12: 94321
NOW Claiming 30% on Ex works price | [7 empty] | 12: 28296.3
10% Claiming after completion | [7 empty] | 12: 9432.11
CGST 9% | [7 empty] | 12: 0
SGST 9% | [7 empty] | 12: 0
Total amount of Invoice | [7 empty] | 12: 28296.3
Total Amount in words Twenty eight thousand two hundred and ninety six rupees only
CERTIFICATE
Certified that the above materials have been supplied by the M/s Vishwanath Projects limited , as shown as per DWA. The same have been stored at GULBARGA
site and using for shifting of consumers Meters from inside to outside the premises of LT installation In Aland Sub-division , Gulbarga Rual Division Under DDUGJY on Total Turnkey Basis.
Certified that the quantitty of materials furnished in the bill verified and these material found as per Gescom specifications.
Certified that we have physically verified the above materials
| Section Officer |  |  |  |  | Asst Executive Engineer(Ele) |  | 10: Executive Engineer (Ele)
| O&M Section |  |  |  |  | O&M Sub Division |  | 10: O&M Rural Dn.No.1
| Madan Hipparga |  |  |  |  | Aland |  | 10: KALABURAGI.

## M Hipp retn.109(A)
TAX INVOICE
RETENTION BILL
Name of the Work: shifting of consumers Meters from inside to outside the premises of LT installation and replacement of existing electromechanical energy meters by static meters in Gulbarga District under DDUGJY on Total Turnkey basis Name of the Contractor: M/s Vishwanath Projects Limited, House No 3-5-874/A, Flat No 401 4th Floor, Hyderguda, Hyderabad (telangana) LOI No & Date: GESCOM/CEE(O)/SEE(Technical) AEE(DDUGJY)/2018-19/62017-30 dt 2-02-2019 DWA No & Date: GESCOM/CEE(O)/SEE(Technical)/AEE(DDUGJY)/INDENT-1037/DWA/2019-20/10023-32 dated 10-05-2019 for Supply and erection portion
5th RETENTION BILL |  |  |  |  | Annexue-I
WORK ORDER NO : DK-33566 Dt: 16.03.2019
INVOICE : VPL/GESCOM/GLB/Meter Shifting/Retn Supply/109/19-20 dt 08-03-2020
Address : Vishwanath Projects Ltd, Hounse No. 1-1495/G/87, C/o. Dr.K.T.Paladi, Goudutai Nagar, Kalaburigi - 585102 |  |  | TEL | 040 - 23211660
|  |  | FAX | 040 - 23210198
|  |  | TIN No | 29370771492
|  |  | CST No | 29370771492
|  |  | GSTIN No | 29AACCV2054N1ZY
To: The Executive Engineer,(O&M) GESCOM. GULBARGA RURAL1 Division, |  |  | Invoice No | VPL/GLB/METER SHIFTING/109/19-20
|  |  | Invoice Date | 08.03.2020
|  |  | Cust.DWA No | GESCOM /CEE(O)/SEE (Technical)/AEE (DDUGJY)/Indent-1037/DWA/2019-20/shifting of Meter (Gulabarga).
|  |  | Cust.DWA Date | 10.05.2019
|  |  | L.R No & Date | Attached
Bank Details: Vishwanath Projects Ltd., Bank Name: ICICI Bank, A/CNO:000851000149 Branch: Khairatabad,hyderabad, IFSC CODE: ICIC0000008 |  |  | Transporter | Attached
Customer Code
|  |  | Customer GSTIN No | 29AABCG8895R1ZD
Customer CST No
Customer TIN No
Sl.No | Particulers |  |  |  | Amount Rs.
1 | Separate Annexure Enclosed of the Station Materials |  |  |  | 94321.1
2 | Freight and Insurance
|  | I) Total Amount Before Tax |  |  | 94321.1
|  | a) Add : CGST |  |  | 0
|  | b) Add : SGST |  |  | 0
c) Add : IGST
|  | II) Tax Amount : GST (a+b+c) |  |  | 0
|  | Now Claiming 30% Grand Total Amount |  |  | 28296
Total Amount in words Twenty eight thousand two hundred and ninety six rupees only |  |  | TERMS OF PAYMENT
|  |  | Retention 10% Amount after Completion |  | 9432.11
|  |  | Net Payable Amount |  | 28296
For Vishwanath Projects Ltd.
Authorised Signatory
Certificate:
Certified that the above materials have been supplied by the TTK contractor of M/S Vishwanth Projects Limited.,
As shown as per DWA, the same have been stored at Kalaburagi,Tq and District Kalaburagi .
site and using for shifting of consumers Meters from inside to outside the premises of LT installation by
and replacement of existing electromechanical energy meters by static meters in Gulbarga District under DDUGJY on Total Turnkey basis
Certified that the quantitty of materials furnished in the bill verified with supporting invoices and these materials found as per Gescom specifications.Certified that we have Physically Verified the above materials
| Section Officer |  | Asst Executive Engineer(Ele) |  | Executive Engineer (Ele)
| O&M Section |  | O&M Sub Division |  | O&M Rural Dn.No.1
| Madan Hipparga |  | Aland |  | KALABURAGI.

## Rudra b ere.110
GULBARGA ELECTRICITY SUPPLY COMPANY LIMITED
Name of the Work :shifting of consumers Meters from inside to outside the premises of LT installation and replacement of existing electromechanical energy meters by static meters in Gulbarga District under DDUGJY on Total Turnkey basis
Name of the Contractor: M/s Vishwanath Projects Limited, House No 3-5-874/A, Flat No 401 4th Floor, Hyderguda, Hyderabad (telangana)
LOI No & Date : GESCOM/CEE(O)/SEE(Technical) AEE(DDUGJY)18-19/62017-30 dt 2-02-2019
DWA No & Date : GESCOM/CEE(O)/SEE(Technical)/AEE(DDUGJY)/INDENT-1037/DWA/2019-20/10023-32 dated 10-05-2019 for Supply and erection portion.
2nd bill ERECTION PORTION | [11 empty] | Annexure-I
Invoice No/Bill No:VPL/GLB/MeterShifting/Erection/110/19-20 dt: 08.03.2020 | [11 empty] | WORK ORDER NO : DK-33565 Dt: 16.03.2019
S.No | Item Description | UOM | HSN CODE | Total Qty | Ex-works Price | GST in Rs | Total amount (Including GST) | Previous Bill caimed Qty | Claimed Qty | Cumulative Qty(Including This Bill) | unit ex works price | ex works price (total) | GST (18%) in Rs | GST Amount In Rs. | Total Value
1 | 2 | 3 |  | 4 | 5a | 5b | 5c=5a=5b | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
ERECTION PORTION :
1 | Deep Drawn Metal Meter Box along with suitable screws for fixing to the wall. | Nos. | 85371000 | 70747 | 6595035.34 | 1187134.66 | 7782170 | 119 | 195 | 314 | 93.22 | 18177.9 | 16.78 | 3272.1 | 21450
Total | [7 empty] | 10: 18177.9; 12: 3272.1; 13: 21450
less 10 % amount payable after completion | [7 empty] | 13: 1817.79
NOW Claiming 90% on Ex works price | [7 empty] | 13: 16360.11
100% Taxes | [7 empty] | 13: 3272.1
Total amount of Invoice | [7 empty] | 13: 19632.21
Total Amount in words Nineteen thousand six hundred and thirty two rupees only
CERTIFICATE
Certified that the above materials have been supplied by the M/s Vishwanath Projects limited , as shown as per DWA. The same have been stored at GULBARGA
site and using for shifting of consumers Meters from inside to outside the premises of LT installation In Aland Sub-division , Gulbarga Rual Division Under DDUGJY on Total Turnkey Basis.
Certified that the quantitty of materials furnished in the bill verified and these material found as per Gescom specifications.
Certified that we have physically verified the above materials
| Section Officer | [5 empty] | Asst Executive Engineer(Ele) | 10: Executive Engineer (Ele)
| O&M Section | [5 empty] | O&M Sub Division | 10: O&M Rural Dn.No.1
| Rudrawadi | [5 empty] | Aland | 10: KALABURAGI.

## Rudra b ere.110(A)
TAX INVOICE
ERECTION BILL
Name of the Work: shifting of consumers Meters from inside to outside the premises of LT installation and replacement of existing electromechanical energy meters by static meters in Gulbarga District under DDUGJY on Total Turnkey basis Name of the Contractor: M/s Vishwanath Projects Limited, House No 3-5-874/A, Flat No 401 4th Floor, Hyderguda, Hyderabad (telangana) LOI No & Date: GESCOM/CEE(O)/SEE(Technical) AEE(DDUGJY)/2018-19/62017-30 dt 2-02-2019 DWA No & Date: GESCOM/CEE(O)/SEE(Technical)/AEE(DDUGJY)/INDENT-1037/DWA/2019-20/10023-32 dated 10-05-2019 for Supply and erection portion
2nd BILL ERECTION PORTION | [5 empty] | Annexure-I
WORK ORDER NO : DK-33565 Dt: 16.03.2019
INVOICE : VPL/GESCOM/GLB/Meter Shifting/Erection/110/19-20 dt 08-03-2020
Address : Vishwanath Projects Ltd, Hounse No. 1-1495/G/87, C/o. Dr.K.T.Paladi, Goudutai Nagar, Kalaburigi - 585102 |  |  |  | TEL | 040 - 23211660
|  |  |  | FAX | 040 - 23210198
|  |  |  | TIN No | 29370771492
|  |  |  | CST No | 29370771492
|  |  |  | GSTIN No | 29AACCV2054N1ZY
To: The Executive Engineer,(O&M) GESCOM. GULBARGA RURAL1 Division, |  |  |  | Invoice No | VPL/GLB/METER SHIFTING/110/19-20
|  |  |  | Invoice Date | 08.03.2020
|  |  |  | Cust.DWA No | GESCOM /CEE(O)/SEE (Technical)/AEE (DDUGJY)/Indent-1037/DWA/2019-20/shifting of Meter (Gulabarga).
|  |  |  | Cust.DWA Date | 10.05.2019
|  |  |  | L.R No & Date | Attached
Bank Details: Vishwanath Projects Ltd., Bank Name: ICICI Bank, A/CNO:000851000149 Branch: Khairatabad,hyderabad, IFSC CODE: ICIC0000008 |  |  |  | Transporter | Attached
Customer Code
|  |  |  | Customer GSTIN No | 29AABCG8895R1ZD
Customer CST No
Customer TIN No
Sl.No | Particulers |  |  |  |  | Amount Rs.
1 | Separate Annexure Enclosed of the Station Materials |  |  |  |  | 18177.9
2 | Freight and Insurance
|  | I) Total Amount Before Tax |  |  |  | 18177.9
|  | a) Add : CGST |  |  |  | 1636.05
|  | b) Add : SGST |  |  |  | 1636.05
c) Add : IGST
|  | II) Tax Amount : GST (a+b+c) |  |  |  | 3272.1
|  | Now Claiming 90% Ex-works ans Total Gst 100% |  |  |  | 19632.21
Total Amount in words Nineteen thousand six hundred and thirty two rupees only |  |  |  | TERMS OF PAYMENT
|  |  |  | Retention 10% Amount after Completion |  | 1817.79
|  |  |  | Net Payable Amount |  | 19632.21
For Vishwanath Projects Ltd.
Authorised Signatory
1. W.O .N O & Date : DK-33565 dt :16-03-2019
2. Estimate Cost : Erection Cost : Rs. 21450 /- |  |  | : Rs. 87120/-
3. Name of the Authority : Executive Engineer( Elect), O&M Division-I, GESCOM, Gulbarga.
4.Name of the Agency : M/S Vishwanath Projects Limited, Hyderabad.
5. Date Of Commencement : 10.05.2019 |  |  |  |  | 6. Date Of Completion : 26.12.2019
7. Date Of Measurment : 10.01.2020 |  |  |  | 8. MB Book No. |  | Page no
1.DI Date : GESCOM /CEE(O)/SEE(Tech)/EEE(DDUGJY)/19-20/13566-81/dt :28-05-2019
2. BG NO: 2423-BG-22-2019 dt .02-03-2019 to 25/11/2020
Certificate:
Certified that the above materials have been supplied by the TTK contractor of M/S Vishwanth Projects Limited.,
As shown as per DWA, the same have been stored at Kalaburagi,Tq and District Kalaburagi .
site and using for shifting of consumers Meters from inside to outside the premises of LT installation
in Aland Sub-Division, Gulbarga Rural Divisional ,Gulbarga District under DDUGJY on Total Turnkey basis
Certified that the quantitty of materials furnished in the bill verified with supporting invoices and these materials found as per Gescom specifications.Certified that we have Physically Verified the above materials
| Section Officer |  |  | Asst Executive Engineer(Ele) |  | Executive Engineer (Ele)
| O&M Section |  |  | O&M Sub Division |  | O&M Rural Dn.No.1
| Rudrawadi |  |  | Aland |  | KALABURAGI.

## Rudra b retn.110
GULBARGA ELECTRICITY SUPPLY COMPANY LIMITED
Name of the Work :shifting of consumers Meters from inside to outside the premises of LT installation and replacement of existing electromechanical energy meters by static meters in Gulbarga District under DDUGJY on Total Turnkey basis
Name of the Contractor: M/s Vishwanath Projects Limited, House No 3-5-874/A, Flat No 401 4th Floor, Hyderguda, Hyderabad (telangana)
LOI No & Date : GESCOM/CEE(O)/SEE(Technical) AEE(DDUGJY)18-19/62017-30 dt 2-02-2019
DWA No & Date : GESCOM/CEE(O)/SEE(Technical)/AEE(DDUGJY)/INDENT-1037/DWA/2019-20/10023-32 dated 10-05-2019 for Supply and erection portion.
2nd RETENTION BILL | [9 empty] | Annexure-I
Invoice No/Bill No:VPL/GLB/Meter Shifting/Retn/110/19-20 dt:08.03.2020 | [9 empty] | WORK ORDER NO : DK-33565 Dt: 16.03.2019
S.No | Item Description | UOM | HSN CODE | Total Qty | Ex-works Price | GST in Rs | Total amount (Including GST) | Previous Bill caimed Qty | Claimed Qty | Cumulative Qty(Including This Bill) | unit ex works price | ex works price (total) | GST (18%) in Rs | Total Value
1 | 2 | 3 |  | 4 | 5a | 5b | 5c=5a=5b | 6 | 7 | 8 | 9 | 10 | 11 | 12
SUPPLY PORTION :
1 | Supply of Deep Drawn Metal Box | Nos. | 85371000 | 70747 | 32975176.7 | 5935673.3 | 38910850 | 119 | 195 | 314 | 466.1 | 90889.5 | 0 | 90889.5
Total | [7 empty] | 10: 90889.5; 12: 90889.5
Total Supply Value | [7 empty] | 12: 90890
NOW Claiming 30% on Ex works price | [7 empty] | 12: 27267
10% Claiming after completion | [7 empty] | 12: 9088.95
CGST 9% | [7 empty] | 12: 0
SGST 9% | [7 empty] | 12: 0
Total amount of Invoice | [7 empty] | 12: 27267
Total Amount in words Twenty seven thousand two hundred and sixty seven rupees only
CERTIFICATE
Certified that the above materials have been supplied by the M/s Vishwanath Projects limited , as shown as per DWA. The same have been stored at GULBARGA
site and using for shifting of consumers Meters from inside to outside the premises of LT installation In Aland Sub-division , Gulbarga Rual Division Under DDUGJY on Total Turnkey Basis.
Certified that the quantitty of materials furnished in the bill verified and these material found as per Gescom specifications.
Certified that we have physically verified the above materials
| Section Officer |  |  |  |  | Asst Executive Engineer(Ele) |  | 10: Executive Engineer (Ele)
| O&M Section |  |  |  |  | O&M Sub Division |  | 10: O&M Rural Dn.No.1
| Rudrawadi |  |  |  |  | Aland |  | 10: KALABURAGI.

## Rudra b retn.110(A)
TAX INVOICE
RETENTION BILL
Name of the Work: shifting of consumers Meters from inside to outside the premises of LT installation and replacement of existing electromechanical energy meters by static meters in Gulbarga District under DDUGJY on Total Turnkey basis Name of the Contractor: M/s Vishwanath Projects Limited, House No 3-5-874/A, Flat No 401 4th Floor, Hyderguda, Hyderabad (telangana) LOI No & Date: GESCOM/CEE(O)/SEE(Technical) AEE(DDUGJY)/2018-19/62017-30 dt 2-02-2019 DWA No & Date: GESCOM/CEE(O)/SEE(Technical)/AEE(DDUGJY)/INDENT-1037/DWA/2019-20/10023-32 dated 10-05-2019 for Supply and erection portion
2nd RETENTION BILL |  |  |  |  | Annexue-I
WORK ORDER NO : DK-33565 Dt: 16.03.2019
INVOICE : VPL/GESCOM/GLB/Meter Shifting/Retn Supply/110/19-20 dt 08-03-2020
Address : Vishwanath Projects Ltd, Hounse No. 1-1495/G/87, C/o. Dr.K.T.Paladi, Goudutai Nagar, Kalaburigi - 585102 |  |  | TEL | 040 - 23211660
|  |  | FAX | 040 - 23210198
|  |  | TIN No | 29370771492
|  |  | CST No | 29370771492
|  |  | GSTIN No | 29AACCV2054N1ZY
To: The Executive Engineer,(O&M) GESCOM. GULBARGA RURAL1 Division, |  |  | Invoice No | VPL/GLB/METER SHIFTING/110/19-20
|  |  | Invoice Date | 08.03.2020
|  |  | Cust.DWA No | GESCOM /CEE(O)/SEE (Technical)/AEE (DDUGJY)/Indent-1037/DWA/2019-20/shifting of Meter (Gulabarga).
|  |  | Cust.DWA Date | 10.05.2019
|  |  | L.R No & Date | Attached
Bank Details: Vishwanath Projects Ltd., Bank Name: ICICI Bank, A/CNO:000851000149 Branch: Khairatabad,hyderabad, IFSC CODE: ICIC0000008 |  |  | Transporter | Attached
Customer Code
|  |  | Customer GSTIN No | 29AABCG8895R1ZD
Customer CST No
Customer TIN No
Sl.No | Particulers |  |  |  | Amount Rs.
1 | Separate Annexure Enclosed of the Station Materials |  |  |  | 90889.5
2 | Freight and Insurance
|  | I) Total Amount Before Tax |  |  | 90889.5
|  | a) Add : CGST |  |  | 0
|  | b) Add : SGST |  |  | 0
c) Add : IGST
|  | II) Tax Amount : GST (a+b+c) |  |  | 0
|  | Now Claiming 30% Grand Total Amount |  |  | 27267
Total Amount in words Twenty seven thousand two hundred and sixty seven rupees only |  |  | TERMS OF PAYMENT
|  |  | Retention 10% Amount after Completion |  | 9088.95
|  |  | Net Payable Amount |  | 27267
For Vishwanath Projects Ltd.
Authorised Signatory
Certificate:
Certified that the above materials have been supplied by the TTK contractor of M/S Vishwanth Projects Limited.,
As shown as per DWA, the same have been stored at Kalaburagi,Tq and District Kalaburagi .
site and using for shifting of consumers Meters from inside to outside the premises of LT installation by
and replacement of existing electromechanical energy meters by static meters in Gulbarga District under DDUGJY on Total Turnkey basis
Certified that the quantitty of materials furnished in the bill verified with supporting invoices and these materials found as per Gescom specifications.Certified that we have Physically Verified the above materials
| Section Officer |  | Asst Executive Engineer(Ele) |  | Executive Engineer (Ele)
| O&M Section |  | O&M Sub Division |  | O&M Rural Dn.No.1
| Rudrawadi |  | Aland |  | KALABURAGI.

## Kotnur ere.111
GULBARGA ELECTRICITY SUPPLY COMPANY LIMITED
Name of the Work :shifting of consumers Meters from inside to outside the premises of LT installation and replacement of existing electromechanical energy meters by static meters in Gulbarga District under DDUGJY on Total Turnkey basis
Name of the Contractor: M/s Vishwanath Projects Limited, House No 3-5-874/A, Flat No 401 4th Floor, Hyderguda, Hyderabad (telangana)
LOI No & Date : GESCOM/CEE(O)/SEE(Technical) AEE(DDUGJY)18-19/62017-30 dt 2-02-2019
DWA No & Date : GESCOM/CEE(O)/SEE(Technical)/AEE(DDUGJY)/INDENT-1037/DWA/2019-20/10023-32 dated 10-05-2019 for Supply and erection portion.
2nd bill ERECTION PORTION | [11 empty] | Annexure-I
Invoice No/Bill No:VPL/GLB/MeterShifting/Erection/111/19-20 dt: 08.03.2020 | [11 empty] | WORK ORDER NO : DK-33578 Dt: 16.03.2019
S.No | Item Description | UOM | HSN CODE | Total Qty | Ex-works Price | GST in Rs | Total amount (Including GST) | Previous Bill caimed Qty | Claimed Qty | Cumulative Qty(Including This Bill) | unit ex works price | ex works price (total) | GST (18%) in Rs | GST Amount In Rs. | Total Value
1 | 2 | 3 |  | 4 | 5a | 5b | 5c=5a=5b | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
ERECTION PORTION :
1 | Deep Drawn Metal Meter Box along with suitable screws for fixing to the wall. | Nos. | 85371000 | 70747 | 6595035.34 | 1187134.66 | 7782170 | 209 | 288 | 497 | 93.22 | 26847.36 | 16.78 | 4832.64 | 31680
Total | [7 empty] | 10: 26847.36; 12: 4832.64; 13: 31680
less 10 % amount payable after completion | [7 empty] | 13: 2684.736
NOW Claiming 90% on Ex works price | [7 empty] | 13: 24162.624
100% Taxes | [7 empty] | 13: 4832.64
Total amount of Invoice | [7 empty] | 13: 28995.264
Total Amount in words Twenty eight thousand nine hundred and ninety five rupees only
CERTIFICATE
Certified that the above materials have been supplied by the M/s Vishwanath Projects limited , as shown as per DWA. The same have been stored at GULBARGA
site and using for shifting of consumers Meters from inside to outside the premises of LT installation In Rural Sub-division , Gulbarga Rual Division Under DDUGJY on Total Turnkey Basis.
Certified that the quantitty of materials furnished in the bill verified and these material found as per Gescom specifications.
Certified that we have physically verified the above materials
| Section Officer | [5 empty] | Asst Executive Engineer(Ele) | 10: Executive Engineer (Ele)
| O&M Section | [5 empty] | O&M Sub Division | 10: O&M Rural Dn.No.1
| Kotnur D | [5 empty] | Rural Sub Division | 10: KALABURAGI.

## kotnur ere.111(A)
TAX INVOICE
ERECTION BILL
Name of the Work: shifting of consumers Meters from inside to outside the premises of LT installation and replacement of existing electromechanical energy meters by static meters in Gulbarga District under DDUGJY on Total Turnkey basis Name of the Contractor: M/s Vishwanath Projects Limited, House No 3-5-874/A, Flat No 401 4th Floor, Hyderguda, Hyderabad (telangana) LOI No & Date: GESCOM/CEE(O)/SEE(Technical) AEE(DDUGJY)/2018-19/62017-30 dt 2-02-2019 DWA No & Date: GESCOM/CEE(O)/SEE(Technical)/AEE(DDUGJY)/INDENT-1037/DWA/2019-20/10023-32 dated 10-05-2019 for Supply and erection portion
2nd BILL ERECTION PORTION | [5 empty] | Annexure-I
WORK ORDER NO : DK-33578 Dt: 16.03.2019
INVOICE : VPL/GESCOM/GLB/Meter Shifting/Erection/111/19-20 dt 08-03-2020
Address : Vishwanath Projects Ltd, Hounse No. 1-1495/G/87, C/o. Dr.K.T.Paladi, Goudutai Nagar, Kalaburigi - 585102 |  |  |  | TEL | 040 - 23211660
|  |  |  | FAX | 040 - 23210198
|  |  |  | TIN No | 29370771492
|  |  |  | CST No | 29370771492
|  |  |  | GSTIN No | 29AACCV2054N1ZY
To: The Executive Engineer,(O&M) GESCOM. GULBARGA RURAL1 Division, |  |  |  | Invoice No | VPL/GLB/METER SHIFTING/111/19-20
|  |  |  | Invoice Date | 08.03.2020
|  |  |  | Cust.DWA No | GESCOM /CEE(O)/SEE (Technical)/AEE (DDUGJY)/Indent-1037/DWA/2019-20/shifting of Meter (Gulabarga).
|  |  |  | Cust.DWA Date | 10.05.2019
|  |  |  | L.R No & Date | Attached
Bank Details: Vishwanath Projects Ltd., Bank Name: ICICI Bank, A/CNO:000851000149 Branch: Khairatabad,hyderabad, IFSC CODE: ICIC0000008 |  |  |  | Transporter | Attached
Customer Code
|  |  |  | Customer GSTIN No | 29AABCG8895R1ZD
Customer CST No
Customer TIN No
Sl.No | Particulers |  |  |  |  | Amount Rs.
1 | Separate Annexure Enclosed of the Station Materials |  |  |  |  | 26847.36
2 | Freight and Insurance
|  | I) Total Amount Before Tax |  |  |  | 26847.36
|  | a) Add : CGST |  |  |  | 2416.32
|  | b) Add : SGST |  |  |  | 2416.32
c) Add : IGST
|  | II) Tax Amount : GST (a+b+c) |  |  |  | 4832.64
|  | Now Claiming 90% Ex-works ans Total Gst 100% |  |  |  | 28995.264
Total Amount in words Twenty eight thousand nine hundred and ninety five rupees only |  |  |  | TERMS OF PAYMENT
|  |  |  | Retention 10% Amount after Completion |  | 2684.736
|  |  |  | Net Payable Amount |  | 28995.264
For Vishwanath Projects Ltd.
Authorised Signatory
1. W.O .N O & Date : DK-33578 dt :16-03-2019
2. Estimate Cost : Erection Cost : Rs. 31680 /- |  |  | : Rs. 87120/-
3. Name of the Authority : Executive Engineer( Elect), O&M Division-I, GESCOM, Gulbarga.
4.Name of the Agency : M/S Vishwanath Projects Limited, Hyderabad.
5. Date Of Commencement : 10.05.2019 |  |  |  |  | 6. Date Of Completion : 29.12.2019
7. Date Of Measurment : 11.01.2020 |  |  |  | 8. MB Book No. |  | Page no
1.DI Date : GESCOM /CEE(O)/SEE(Tech)/EEE(DDUGJY)/19-20/13566-81/dt :28-05-2019
2. BG NO: 2423-BG-22-2019 dt .02-03-2019 to 25/11/2020
Certificate:
Certified that the above materials have been supplied by the TTK contractor of M/S Vishwanth Projects Limited.,
As shown as per DWA, the same have been stored at Kalaburagi,Tq and District Kalaburagi .
site and using for shifting of consumers Meters from inside to outside the premises of LT installation
in Rural Sub-Division, Gulbarga Rural Divisional ,Gulbarga District under DDUGJY on Total Turnkey basis
Certified that the quantitty of materials furnished in the bill verified with supporting invoices and these materials found as per Gescom specifications.Certified that we have Physically Verified the above materials
| Section Officer |  |  | Asst Executive Engineer(Ele) |  | Executive Engineer (Ele)
| O&M Section |  |  | O&M Sub Division |  | O&M Rural Dn.No.1
| Kotnur D |  |  | Rural Sub Division |  | KALABURAGI.

## kotnur retn.111
GULBARGA ELECTRICITY SUPPLY COMPANY LIMITED
Name of the Work :shifting of consumers Meters from inside to outside the premises of LT installation and replacement of existing electromechanical energy meters by static meters in Gulbarga District under DDUGJY on Total Turnkey basis
Name of the Contractor: M/s Vishwanath Projects Limited, House No 3-5-874/A, Flat No 401 4th Floor, Hyderguda, Hyderabad (telangana)
LOI No & Date : GESCOM/CEE(O)/SEE(Technical) AEE(DDUGJY)18-19/62017-30 dt 2-02-2019
DWA No & Date : GESCOM/CEE(O)/SEE(Technical)/AEE(DDUGJY)/INDENT-1037/DWA/2019-20/10023-32 dated 10-05-2019 for Supply and erection portion.
2nd RETENTION BILL | [9 empty] | Annexure-I
Invoice No/Bill No:VPL/GLB/Meter Shifting/Retn/111/19-20 dt:08.03.2020 | [9 empty] | WORK ORDER NO : DK-33578 Dt: 16.03.2019
S.No | Item Description | UOM | HSN CODE | Total Qty | Ex-works Price | GST in Rs | Total amount (Including GST) | Previous Bill caimed Qty | Claimed Qty | Cumulative Qty(Including This Bill) | unit ex works price | ex works price (total) | GST (18%) in Rs | Total Value
1 | 2 | 3 |  | 4 | 5a | 5b | 5c=5a=5b | 6 | 7 | 8 | 9 | 10 | 11 | 12
SUPPLY PORTION :
1 | Supply of Deep Drawn Metal Box | Nos. | 85371000 | 70747 | 32975176.7 | 5935673.3 | 38910850 | 209 | 288 | 497 | 466.1 | 134236.8 | 0 | 134236.8
Total | [7 empty] | 10: 134236.8; 12: 134236.8
Total Supply Value | [7 empty] | 12: 134237
NOW Claiming 30% on Ex works price | [7 empty] | 12: 40271.1
10% Claiming after completion | [7 empty] | 12: 13423.68
CGST 9% | [7 empty] | 12: 0
SGST 9% | [7 empty] | 12: 0
Total amount of Invoice | [7 empty] | 12: 40271.1
Total Amount in words Fourty thousand two hundred and seventy one rupees only
CERTIFICATE
Certified that the above materials have been supplied by the M/s Vishwanath Projects limited , as shown as per DWA. The same have been stored at GULBARGA
site and using for shifting of consumers Meters from inside to outside the premises of LT installation In Rural Sub-division , Gulbarga Rual Division Under DDUGJY on Total Turnkey Basis.
Certified that the quantitty of materials furnished in the bill verified and these material found as per Gescom specifications.
Certified that we have physically verified the above materials
| Section Officer |  |  |  |  | Asst Executive Engineer(Ele) |  | 10: Executive Engineer (Ele)
| O&M Section |  |  |  |  | O&M Sub Division |  | 10: O&M Rural Dn.No.1
| Kotnur D |  |  |  |  | Rural Sub Division |  | 10: KALABURAGI.

## kotnur retn.111(A)
TAX INVOICE
RETENTION BILL
Name of the Work: shifting of consumers Meters from inside to outside the premises of LT installation and replacement of existing electromechanical energy meters by static meters in Gulbarga District under DDUGJY on Total Turnkey basis Name of the Contractor: M/s Vishwanath Projects Limited, House No 3-5-874/A, Flat No 401 4th Floor, Hyderguda, Hyderabad (telangana) LOI No & Date: GESCOM/CEE(O)/SEE(Technical) AEE(DDUGJY)/2018-19/62017-30 dt 2-02-2019 DWA No & Date: GESCOM/CEE(O)/SEE(Technical)/AEE(DDUGJY)/INDENT-1037/DWA/2019-20/10023-32 dated 10-05-2019 for Supply and erection portion
2nd RETENTION BILL |  |  |  |  | Annexue-I
WORK ORDER NO : DK-33578 Dt: 16.03.2019
INVOICE : VPL/GESCOM/GLB/Meter Shifting/Retn Supply/111/19-20 dt 08-03-2020
Address : Vishwanath Projects Ltd, Hounse No. 1-1495/G/87, C/o. Dr.K.T.Paladi, Goudutai Nagar, Kalaburigi - 585102 |  |  | TEL | 040 - 23211660
|  |  | FAX | 040 - 23210198
|  |  | TIN No | 29370771492
|  |  | CST No | 29370771492
|  |  | GSTIN No | 29AACCV2054N1ZY
To: The Executive Engineer,(O&M) GESCOM. GULBARGA RURAL1 Division, |  |  | Invoice No | VPL/GLB/METER SHIFTING/111/19-20
|  |  | Invoice Date | 08.03.2020
|  |  | Cust.DWA No | GESCOM /CEE(O)/SEE (Technical)/AEE (DDUGJY)/Indent-1037/DWA/2019-20/shifting of Meter (Gulabarga).
|  |  | Cust.DWA Date | 10.05.2019
|  |  | L.R No & Date | Attached
Bank Details: Vishwanath Projects Ltd., Bank Name: ICICI Bank, A/CNO:000851000149 Branch: Khairatabad,hyderabad, IFSC CODE: ICIC0000008 |  |  | Transporter | Attached
Customer Code
|  |  | Customer GSTIN No | 29AABCG8895R1ZD
Customer CST No
Customer TIN No
Sl.No | Particulers |  |  |  | Amount Rs.
1 | Separate Annexure Enclosed of the Station Materials |  |  |  | 134236.8
2 | Freight and Insurance
|  | I) Total Amount Before Tax |  |  | 134236.8
|  | a) Add : CGST |  |  | 0
|  | b) Add : SGST |  |  | 0
c) Add : IGST
|  | II) Tax Amount : GST (a+b+c) |  |  | 0
|  | Now Claiming 30% Grand Total Amount |  |  | 40271
Total Amount in words Fourty thousand two hundred and seventy one rupees only |  |  | TERMS OF PAYMENT
|  |  | Retention 10% Amount after Completion |  | 13423.68
|  |  | Net Payable Amount |  | 40271
For Vishwanath Projects Ltd.
Authorised Signatory
Certificate:
Certified that the above materials have been supplied by the TTK contractor of M/S Vishwanth Projects Limited.,
As shown as per DWA, the same have been stored at Kalaburagi,Tq and District Kalaburagi .
site and using for shifting of consumers Meters from inside to outside the premises of LT installation by
and replacement of existing electromechanical energy meters by static meters in Gulbarga District under DDUGJY on Total Turnkey basis
Certified that the quantitty of materials furnished in the bill verified with supporting invoices and these materials found as per Gescom specifications.Certified that we have Physically Verified the above materials
| Section Officer |  | Asst Executive Engineer(Ele) |  | Executive Engineer (Ele)
| O&M Section |  | O&M Sub Division |  | O&M Rural Dn.No.1
| Kotnur D |  | Rural Sub Division |  | KALABURAGI.

## VK Sal ere.112
GULBARGA ELECTRICITY SUPPLY COMPANY LIMITED
Name of the Work :shifting of consumers Meters from inside to outside the premises of LT installation and replacement of existing electromechanical energy meters by static meters in Gulbarga District under DDUGJY on Total Turnkey basis
Name of the Contractor: M/s Vishwanath Projects Limited, House No 3-5-874/A, Flat No 401 4th Floor, Hyderguda, Hyderabad (telangana)
LOI No & Date : GESCOM/CEE(O)/SEE(Technical) AEE(DDUGJY)18-19/62017-30 dt 2-02-2019
DWA No & Date : GESCOM/CEE(O)/SEE(Technical)/AEE(DDUGJY)/INDENT-1037/DWA/2019-20/10023-32 dated 10-05-2019 for Supply and erection portion.
1st bill ERECTION PORTION | [11 empty] | Annexure-I
Invoice No/Bill No:VPL/GLB/MeterShifting/ Erection/112/19-20 dt: 08.03.2020 | [11 empty] | WORK ORDER NO : DK-33586 Dt: 16.03.2019
S.No | Item Description | UOM | HSN CODE | Total Qty | Ex-works Price | GST in Rs | Total amount (Including GST) | Previous Bill caimed Qty | Claimed Qty | Cumulative Qty(Including This Bill) | unit ex works price | ex works price (total) | GST (18%) in Rs | GST Amount In Rs. | Total Value
1 | 2 | 3 |  | 4 | 5a | 5b | 5c=5a=5b | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
ERECTION PORTION :
1 | Deep Drawn Metal Meter Box along with suitable screws for fixing to the wall. | Nos. | 85371000 | 70747 | 6595035.34 | 1187134.66 | 7782170 | 0 | 394 | 394 | 93.22 | 36728.68 | 16.78 | 6611.32 | 43340
Total | [7 empty] | 10: 36728.68; 12: 6611.32; 13: 43340
less 10 % amount payable after completion | [7 empty] | 13: 3672.868
NOW Claiming 90% on Ex works price | [7 empty] | 13: 33055.812
100% Taxes | [7 empty] | 13: 6611.32
Total amount of Invoice | [7 empty] | 13: 39667.132
Total Amount in words Thirty nine thousand six hundred and sixty seven rupees only
CERTIFICATE
Certified that the above materials have been supplied by the M/s Vishwanath Projects limited , as shown as per DWA. The same have been stored at GULBARGA
site and using for shifting of consumers Meters from inside to outside the premises of LT installation In Kadaganchi Sub-division , Gulbarga Rual Division Under DDUGJY on Total Turnkey Basis.
Certified that the quantitty of materials furnished in the bill verified and these material found as per Gescom specifications.
Certified that we have physically verified the above materials
| Section Officer | [5 empty] | Asst Executive Engineer(Ele) | 10: Executive Engineer (Ele)
| O&M Section | [5 empty] | O&M Sub Division | 10: O&M Rural Dn.No.1
| V K Salagar | [5 empty] | Kadaganchi | 10: Kalaburagi

## VK Sal ere.112(A)
TAX INVOICE
ERECTION BILL
Name of the Work: shifting of consumers Meters from inside to outside the premises of LT installation and replacement of existing electromechanical energy meters by static meters in Gulbarga District under DDUGJY on Total Turnkey basis Name of the Contractor: M/s Vishwanath Projects Limited, House No 3-5-874/A, Flat No 401 4th Floor, Hyderguda, Hyderabad (telangana) LOI No & Date: GESCOM/CEE(O)/SEE(Technical) AEE(DDUGJY)/2018-19/62017-30 dt 2-02-2019 DWA No & Date: GESCOM/CEE(O)/SEE(Technical)/AEE(DDUGJY)/INDENT-1037/DWA/2019-20/10023-32 dated 10-05-2019 for Supply and erection portion
1st BILL ERECTION PORTION |  |  |  |  | Annexure-I
WORK ORDER NO : DK-33586 Dt: 16.03.2019
INVOICE : VPL/GESCOM/GLB/Meter Shifting/Erection/112/19-20 dt 08-03-2020
Address : Vishwanath Projects Ltd, Hounse No. 1-1495/G/87, C/o. Dr.K.T.Paladi, Goudutai Nagar, Kalaburigi - 585102 |  |  | TEL | 040 - 23211660
|  |  | FAX | 040 - 23210198
|  |  | TIN No | 29370771492
|  |  | CST No | 29370771492
|  |  | GSTIN No | 29AACCV2054N1ZY
To: The Executive Engineer,(O&M) GESCOM. GULBARGA RURAL1 Division, |  |  | Invoice No | VPL/GLB/METER SHIFTING/112/19-20
|  |  | Invoice Date | 08.03.2020
|  |  | Cust.DWA No | GESCOM /CEE(O)/SEE (Technical)/AEE (DDUGJY)/Indent-1037/DWA/2019-20/shifting of Meter (Gulabarga).
|  |  | Cust.DWA Date | 10.05.2019
|  |  | L.R No & Date | Attached
Bank Details: Vishwanath Projects Ltd., Bank Name: ICICI Bank, A/CNO:000851000149 Branch: Khairatabad,hyderabad, IFSC CODE: ICIC0000008 |  |  | Transporter | Attached
Customer Code
|  |  | Customer GSTIN No | 29AABCG8895R1ZD
Customer CST No
Customer TIN No
Sl.No | Particulers |  |  |  | Amount Rs.
1 | Separate Annexure Enclosed of the Station Materials |  |  |  | 36728.68
2 | Freight and Insurance
|  | I) Total Amount Before Tax |  |  | 36728.68
|  | a) Add : CGST |  |  | 3305.66
|  | b) Add : SGST |  |  | 3305.66
c) Add : IGST
|  | II) Tax Amount : GST (a+b+c) |  |  | 6611.32
|  | Now Claiming 90% Ex-works ans Total Gst 100% |  |  | 39667.132
Total Amount in words Thirty nine thousand six hundred and sixty seven rupees only |  |  | TERMS OF PAYMENT
|  |  | Retention 10% Amount after Completion |  | 3672.868
|  |  | Net Payable Amount |  | 39667
For Vishwanath Projects Ltd.
Authorised Signatory
1. W.O .N O & Date : DK-33586 dt :16-03-2019
2. Estimate Cost : Erection Cost : Rs. 43340 /-
3. Name of the Authority : Executive Engineer( Elect), O&M Division-I, GESCOM, Gulbarga.
4.Name of the Agency : M/S Vishwanath Projects Limited, Hyderabad.
5. Date Of Commencement : 10.05.2019 |  |  |  | 6. Date Of Completion : 20.12.2019
7. Date Of Measurment : 16.01.2020 |  |  | 8. MB Book No. |  | Page no
1.DI Date : GESCOM /CEE(O)/SEE(Tech)/EEE(DDUGJY)/19-20/13566-81/dt :28-05-2019
2. BG NO: 2423-BG-22-2019 dt .02-03-2019 to 25/11/2020
Certificate:
Certified that the above materials have been supplied by the TTK contractor of M/S Vishwanth Projects Limited.,
As shown as per DWA, the same have been stored at Kalaburagi,Tq and District Kalaburagi .
site and using for shifting of consumers Meters from inside to outside the premises of LT installation
in Kadaganchi Sub-Division, Gulbarga Rural Divisional ,Gulbarga District under DDUGJY on Total Turnkey basis
Certified that the quantitty of materials furnished in the bill verified with supporting invoices and these materials found as per Gescom specifications.Certified that we have Physically Verified the above materials
| Section Officer |  | Asst Executive Engineer(Ele) |  | Executive Engineer (Ele)
| O&M Section |  | O&M Sub Division |  | O&M Rural Division-1
| V K Salagar |  | Kadaganchi |  | Kalaburagi

## VK Sal retn.112
GULBARGA ELECTRICITY SUPPLY COMPANY LIMITED
Name of the Work :shifting of consumers Meters from inside to outside the premises of LT installation and replacement of existing electromechanical energy meters by static meters in Gulbarga District under DDUGJY on Total Turnkey basis
Name of the Contractor: M/s Vishwanath Projects Limited, House No 3-5-874/A, Flat No 401 4th Floor, Hyderguda, Hyderabad (telangana)
LOI No & Date : GESCOM/CEE(O)/SEE(Technical) AEE(DDUGJY)18-19/62017-30 dt 2-02-2019
DWA No & Date : GESCOM/CEE(O)/SEE(Technical)/AEE(DDUGJY)/INDENT-1037/DWA/2019-20/10023-32 dated 10-05-2019 for Supply and erection portion.
1st RETENTION BILL | [9 empty] | Annexure-I
Invoice No/Bill No:VPL/GLB/Meter Shifting/ Retn/112/19-20 dt: 08.03.2020 | [9 empty] | WORK ORDER NO : DK-33586 Dt: 16.03.2019
S.No | Item Description | UOM | HSN CODE | Total Qty | Ex-works Price | GST in Rs | Total amount (Including GST) | Previous Bill caimed Qty | Claimed Qty | Cumulative Qty(Including This Bill) | unit ex works price | ex works price (total) | GST (18%) in Rs | Total Value
1 | 2 | 3 |  | 4 | 5a | 5b | 5c=5a=5b | 6 | 7 | 8 | 9 | 10 | 11 | 12
SUPPLY PORTION :
1 | Supply of Deep Drawn Metal Box | Nos. | 85371000 | 70747 | 32975176.7 | 5935673.3 | 38910850 | 0 | 394 | 394 | 466.1 | 183643.4 | 0 | 183643.4
Total | [7 empty] | 10: 183643.4; 12: 183643.4
Total Supply Value | [7 empty] | 12: 183643
NOW Claiming 30% on Ex works price | [7 empty] | 12: 55092.9
10% Claiming after completion | [7 empty] | 12: 18364.34
CGST 9% | [7 empty] | 12: 0
SGST 9% | [7 empty] | 12: 0
Total amount of Invoice | [7 empty] | 12: 55092.9
Total Amount in words Fifty five thousand ninety three rupees only
CERTIFICATE
Certified that the above materials have been supplied by the M/s Vishwanath Projects limited , as shown as per DWA. The same have been stored at GULBARGA
site and using for shifting of consumers Meters from inside to outside the premises of LT installation In Kadaganchi Sub-division , Gulbarga Rual Division Under DDUGJY on Total Turnkey Basis.
Certified that the quantitty of materials furnished in the bill verified and these material found as per Gescom specifications.
Certified that we have physically verified the above materials
| Section Officer |  |  |  |  | Asst Executive Engineer(Ele) |  | 10: Executive Engineer (Ele)
| O&M Section |  |  |  |  | O&M Sub Division |  | 10: O&M Rural Division-1
| V K Salagar |  |  |  |  | Kadaganchi |  | 10: Kalaburagi

## VK Sal retn.112(A)
TAX INVOICE
RETENTION BILL
Name of the Work: shifting of consumers Meters from inside to outside the premises of LT installation and replacement of existing electromechanical energy meters by static meters in Gulbarga District under DDUGJY on Total Turnkey basis Name of the Contractor: M/s Vishwanath Projects Limited, House No 3-5-874/A, Flat No 401 4th Floor, Hyderguda, Hyderabad (telangana) LOI No & Date: GESCOM/CEE(O)/SEE(Technical) AEE(DDUGJY)/2018-19/62017-30 dt 2-02-2019 DWA No & Date: GESCOM/CEE(O)/SEE(Technical)/AEE(DDUGJY)/INDENT-1037/DWA/2019-20/10023-32 dated 10-05-2019 for Supply and erection portion
1st RETENTION BILL |  |  |  |  | Annexue-I
WORK ORDER NO : DK-33586 Dt: 16.03.2019
INVOICE : VPL/GESCOM/GLB/Meter Shifting/Retn Supply/112/19-20 dt 08-03-2020
Address : Vishwanath Projects Ltd, Hounse No. 1-1495/G/87, C/o. Dr.K.T.Paladi, Goudutai Nagar, Kalaburigi - 585102 |  |  | TEL | 040 - 23211660
|  |  | FAX | 040 - 23210198
|  |  | TIN No | 29370771492
|  |  | CST No | 29370771492
|  |  | GSTIN No | 29AACCV2054N1ZY
To: The Executive Engineer,(O&M) GESCOM. GULBARGA RURAL1 Division, |  |  | Invoice No | VPL/GLB/METER SHIFTING/112/19-20
|  |  | Invoice Date | 08.03.2020
|  |  | Cust.DWA No | GESCOM /CEE(O)/SEE (Technical)/AEE (DDUGJY)/Indent-1037/DWA/2019-20/shifting of Meter (Gulabarga).
|  |  | Cust.DWA Date | 10.05.2019
|  |  | L.R No & Date | Attached
Bank Details: Vishwanath Projects Ltd., Bank Name: ICICI Bank, A/CNO:000851000149 Branch: Khairatabad,hyderabad, IFSC CODE: ICIC0000008 |  |  | Transporter | Attached
Customer Code
|  |  | Customer GSTIN No | 29AABCG8895R1ZD
Customer CST No
Customer TIN No
Sl.No | Particulers |  |  |  | Amount Rs.
1 | Separate Annexure Enclosed of the Station Materials |  |  |  | 183643
2 | Freight and Insurance
|  | I) Total Amount Before Tax |  |  | 183643
|  | a) Add : CGST |  |  | 0
|  | b) Add : SGST |  |  | 0
c) Add : IGST
|  | II) Tax Amount : GST (a+b+c) |  |  | 0
|  | Now Claiming 30% Grand Total Amount |  |  | 55093
Total Amount in words Fifty five thousand ninety three rupees only |  |  | TERMS OF PAYMENT
|  |  | Retention 10% Amount after Completion |  | 18364.3
|  |  | Net Payable Amount |  | 55093
For Vishwanath Projects Ltd.
Authorised Signatory
Certificate:
Certified that the above materials have been supplied by the TTK contractor of M/S Vishwanth Projects Limited.,
As shown as per DWA, the same have been stored at Kalaburagi,Tq and District Kalaburagi .
site and using for shifting of consumers Meters from inside to outside the premises of LT installation by
and replacement of existing electromechanical energy meters by static meters in Gulbarga District under DDUGJY on Total Turnkey basis
Certified that the quantitty of materials furnished in the bill verified with supporting invoices and these materials found as per Gescom specifications.Certified that we have Physically Verified the above materials
| Section Officer |  | Asst Executive Engineer(Ele) |  | Executive Engineer (Ele)
| O&M Section |  | O&M Sub Division |  | O&M Rural Division-1
| V K Salagar |  | Kadaganchi |  | Kalaburagi

## Kadag ere.113
GULBARGA ELECTRICITY SUPPLY COMPANY LIMITED
Name of the Work :shifting of consumers Meters from inside to outside the premises of LT installation and replacement of existing electromechanical energy meters by static meters in Gulbarga District under DDUGJY on Total Turnkey basis
Name of the Contractor: M/s Vishwanath Projects Limited, House No 3-5-874/A, Flat No 401 4th Floor, Hyderguda, Hyderabad (telangana)
LOI No & Date : GESCOM/CEE(O)/SEE(Technical) AEE(DDUGJY)18-19/62017-30 dt 2-02-2019
DWA No & Date : GESCOM/CEE(O)/SEE(Technical)/AEE(DDUGJY)/INDENT-1037/DWA/2019-20/10023-32 dated 10-05-2019 for Supply and erection portion.
5th bill ERECTION PORTION | [11 empty] | Annexure-I
Invoice No/Bill No:VPL/GLB/MeterShifting/ Erection/113/19-20 dt: 09.03.2020 | [11 empty] | WORK ORDER NO : DK-33583 Dt: 16.03.2019
S.No | Item Description | UOM | HSN CODE | Total Qty | Ex-works Price | GST in Rs | Total amount (Including GST) | Previous Bill caimed Qty | Claimed Qty | Cumulative Qty(Including This Bill) | unit ex works price | ex works price (total) | GST (18%) in Rs | GST Amount In Rs. | Total Value
1 | 2 | 3 |  | 4 | 5a | 5b | 5c=5a=5b | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
ERECTION PORTION :
1 | Deep Drawn Metal Meter Box along with suitable screws for fixing to the wall. | Nos. | 85371000 | 118777 | 11072391.94 | 1993078.06 | 13065470 | 4148 | 65 | 4213 | 93.22 | 6059.3 | 16.78 | 1090.7 | 7150
2 | Realeasing and refixing of meter | Nos. | 39174000 | 118777 | 17816550 | 3206979 | 21023529 | 4148 | 65 | 4213 | 150 | 9750 | 27 | 1755 | 11505
3 | Fixing heavy gauge PVC Pipes using inverted wood plugs in case of RCC ceiling and RCC wall stone structure of raw plugs in case of brick walls and cement palstering damaged portion using heavy gauge saddles at an interval of 700 mm using NF screws (2/1) | Nos. | 85444999 | 118777 | 27882900.75 | 5018328.25 | 32901229 | 4148 | 65 | 4213 | 234.75 | 15258.75 | 42.25 | 2746.25 | 18005
Total | [7 empty] | 10: 31068.05; 12: 5591.95; 13: 36660
less 10 % amount payable after completion | [7 empty] | 13: 3106.805
NOW Claiming 90% on Ex works price | [7 empty] | 13: 27961.245
100% Taxes | [7 empty] | 13: 5591.95
Total amount of Invoice | [7 empty] | 13: 33553.195
Total Amount in words Thirty three thousand five hundred and fifty three rupees only
CERTIFICATE
Certified that the above materials have been supplied by the M/s Vishwanath Projects limited , as shown as per DWA. The same have been stored at GULBARGA
site and using for shifting of consumers Meters from inside to outside the premises of LT installation In Kadaganchi Sub-division , Gulbarga Rual Division Under DDUGJY on Total Turnkey Basis.
Certified that the quantitty of materials furnished in the bill verified and these material found as per Gescom specifications.
Certified that we have physically verified the above materials
| Section Officer | [5 empty] | Asst Executive Engineer(Ele) | 10: Executive Engineer (Ele)
| O&M Section | [5 empty] | O&M Sub Division | 10: O&M Rural Dn.No.1
| Kadaganchi | [5 empty] | Kadaganchi | 10: KALABURAGI.

## Kadag ere.113(A)
TAX INVOICE
ERECTION BILL
Name of the Work: shifting of consumers Meters from inside to outside the premises of LT installation and replacement of existing electromechanical energy meters by static meters in Gulbarga District under DDUGJY on Total Turnkey basis Name of the Contractor: M/s Vishwanath Projects Limited, House No 3-5-874/A, Flat No 401 4th Floor, Hyderguda, Hyderabad (telangana) LOI No & Date: GESCOM/CEE(O)/SEE(Technical) AEE(DDUGJY)/2018-19/62017-30 dt 2-02-2019 DWA No & Date: GESCOM/CEE(O)/SEE(Technical)/AEE(DDUGJY)/INDENT-1037/DWA/2019-20/10023-32 dated 10-05-2019 for Supply and erection portion
5th BILL ERECTION PORTION |  |  |  |  | Annexure-I
WORK ORDER NO : DK-33583 Dt: 16.03.2019
INVOICE : VPL/GESCOM/GLB/Meter Shifting/Erection/113/19-20 dt 09-03-2020
Address : Vishwanath Projects Ltd, Hounse No. 1-1495/G/87, C/o. Dr.K.T.Paladi, Goudutai Nagar, Kalaburigi - 585102 |  |  | TEL | 040 - 23211660
|  |  | FAX | 040 - 23210198
|  |  | TIN No | 29370771492
|  |  | CST No | 29370771492
|  |  | GSTIN No | 29AACCV2054N1ZY
To: The Executive Engineer,(O&M) GESCOM. GULBARGA RURAL1 Division, |  |  | Invoice No | VPL/GLB/METER SHIFTING/113/19-20
|  |  | Invoice Date | 09.03.2020
|  |  | Cust.DWA No | GESCOM /CEE(O)/SEE (Technical)/AEE (DDUGJY)/Indent-1037/DWA/2019-20/shifting of Meter (Gulabarga).
|  |  | Cust.DWA Date | 10.05.2019
|  |  | L.R No & Date | Attached
Bank Details: Vishwanath Projects Ltd., Bank Name: ICICI Bank, A/CNO:000851000149 Branch: Khairatabad,hyderabad, IFSC CODE: ICIC0000008 |  |  | Transporter | Attached
Customer Code
|  |  | Customer GSTIN No | 29AABCG8895R1ZD
Customer CST No
Customer TIN No
Sl.No | Particulers |  |  |  | Amount Rs.
1 | Separate Annexure Enclosed of the Station Materials |  |  |  | 31068.05
2 | Freight and Insurance
|  | I) Total Amount Before Tax |  |  | 31068.05
|  | a) Add : CGST |  |  | 2795.975
|  | b) Add : SGST |  |  | 2795.975
c) Add : IGST
|  | II) Tax Amount : GST (a+b+c) |  |  | 5591.95
|  | Now Claiming 90% Ex-works ans Total Gst 100% |  |  | 33553.195
Total Amount in words Thirty three thousand five hundred and fifty three rupees only |  |  | TERMS OF PAYMENT
|  |  | Retention 10% Amount after Completion |  | 3106.805
|  |  | Net Payable Amount |  | 33553
For Vishwanath Projects Ltd.
Authorised Signatory
1. W.O .N O & Date : DK-33583 dt :16-03-2019
2. Estimate Cost : Erection Cost : Rs. 36660 /-
3. Name of the Authority : Executive Engineer( Elect), O&M Division-I, GESCOM, Gulbarga.
4.Name of the Agency : M/S Vishwanath Projects Limited, Hyderabad.
5. Date Of Commencement : 10.05.2019 |  |  |  | 6. Date Of Completion : 22.12.2019
7. Date Of Measurment : 19.01.2020 |  |  | 8. MB Book No. |  | Page no
1.DI Date : GESCOM /CEE(O)/SEE(Tech)/EEE(DDUGJY)/19-20/13566-81/dt :28-05-2019
2. BG NO: 2423-BG-22-2019 dt .02-03-2019 to 25/11/2020
Certificate:
Certified that the above materials have been supplied by the TTK contractor of M/S Vishwanth Projects Limited.,
As shown as per DWA, the same have been stored at Kalaburagi,Tq and District Kalaburagi .
site and using for shifting of consumers Meters from inside to outside the premises of LT installation
in Kadaganchi Sub-Division, Gulbarga Rural Divisional ,Gulbarga District under DDUGJY on Total Turnkey basis
Certified that the quantitty of materials furnished in the bill verified with supporting invoices and these materials found as per Gescom specifications.Certified that we have Physically Verified the above materials
| Section Officer |  | Asst Executive Engineer(Ele) |  | Executive Engineer (Ele)
| O&M Section |  | O&M Sub Division |  | O&M Rural Dn.No.1
| Kadaganchi |  | Kadaganchi |  | KALABURAGI.

## Kadag retn.113
GULBARGA ELECTRICITY SUPPLY COMPANY LIMITED
Name of the Work :shifting of consumers Meters from inside to outside the premises of LT installation and replacement of existing electromechanical energy meters by static meters in Gulbarga District under DDUGJY on Total Turnkey basis
Name of the Contractor: M/s Vishwanath Projects Limited, House No 3-5-874/A, Flat No 401 4th Floor, Hyderguda, Hyderabad (telangana)
LOI No & Date : GESCOM/CEE(O)/SEE(Technical) AEE(DDUGJY)18-19/62017-30 dt 2-02-2019
DWA No & Date : GESCOM/CEE(O)/SEE(Technical)/AEE(DDUGJY)/INDENT-1037/DWA/2019-20/10023-32 dated 10-05-2019 for Supply and erection portion.
5th RETENTION BILL | [9 empty] | Annexure-I
Invoice No/Bill No:VPL/GLB/Meter Shifting/ Retn/113/19-20 dt: 09.03.2020 | [9 empty] | WORK ORDER NO : DK-33583 Dt: 16.03.2019
S.No | Item Description | UOM | HSN CODE | Total Qty | Ex-works Price | GST in Rs | Total amount (Including GST) | Previous Bill caimed Qty | Claimed Qty | Cumulative Qty(Including This Bill) | unit ex works price | ex works price (total) | GST (18%) in Rs | Total Value
1 | 2 | 3 |  | 4 | 5a | 5b | 5c=5a=5b | 6 | 7 | 8 | 9 | 10 | 11 | 12
SUPPLY PORTION :
1 | Supply of Deep Drawn Metal Box | Nos. | 85371000 | 118777 | 55361959.7 | 9965390.3 | 65327350 | 4148 | 65 | 4213 | 466.1 | 30296.5 | 0 | 30296.5
2 | Supply of Heavy gauge PVC conduit pipe 25mm dia 2mm thick. | Mtr | 39174000 | 1187770 | 21641169.4 | 3895885.6 | 25537055 | 41480 | 650 | 42130 | 18.22 | 11843 | 0 | 11843
3 | Supply wiring for lighting/power circuit using one of PVC insulated 1.1 kv class standed Aluminium 6 sqmm single core | Mtr | 85444999 | 2375540 | 22140032.8 | 3990907.2 | 26130940 | 82960 | 1300 | 84260 | 9.32 | 12116 | 0 | 12116
Total | [7 empty] | 10: 54255.5; 12: 54255.5
Total Supply Value | [7 empty] | 12: 54256
NOW Claiming 30% on Ex works price | [7 empty] | 12: 16276.8
10% Claiming after completion | [7 empty] | 12: 5425.55
CGST 9% | [7 empty] | 12: 0
SGST 9% | [7 empty] | 12: 0
Total amount of Invoice | [7 empty] | 12: 16276.8
Total Amount in words Sixteen thousand two hundred and seventy seven rupees only
CERTIFICATE
Certified that the above materials have been supplied by the M/s Vishwanath Projects limited , as shown as per DWA. The same have been stored at GULBARGA
site and using for shifting of consumers Meters from inside to outside the premises of LT installation In Kadaganchi Sub-division , Gulbarga Rual Division Under DDUGJY on Total Turnkey Basis.
Certified that the quantitty of materials furnished in the bill verified and these material found as per Gescom specifications.
Certified that we have physically verified the above materials
| Section Officer |  |  |  |  | Asst Executive Engineer(Ele) |  | 10: Executive Engineer (Ele)
| O&M Section |  |  |  |  | O&M Sub Division |  | 10: O&M Rural Dn.No.1
| Kadaganchi |  |  |  |  | Kadaganchi |  | 10: KALABURAGI.

## Kadag retn.113(A)
TAX INVOICE
RETENTION BILL
Name of the Work: shifting of consumers Meters from inside to outside the premises of LT installation and replacement of existing electromechanical energy meters by static meters in Gulbarga District under DDUGJY on Total Turnkey basis Name of the Contractor: M/s Vishwanath Projects Limited, House No 3-5-874/A, Flat No 401 4th Floor, Hyderguda, Hyderabad (telangana) LOI No & Date: GESCOM/CEE(O)/SEE(Technical) AEE(DDUGJY)/2018-19/62017-30 dt 2-02-2019 DWA No & Date: GESCOM/CEE(O)/SEE(Technical)/AEE(DDUGJY)/INDENT-1037/DWA/2019-20/10023-32 dated 10-05-2019 for Supply and erection portion
5th RETENTION BILL |  |  |  |  | Annexue-I
WORK ORDER NO : DK-33583 Dt: 16.03.2019
INVOICE : VPL/GESCOM/GLB/Meter Shifting/Retn Supply/113/19-20 dt 09-03-2020
Address : Vishwanath Projects Ltd, Hounse No. 1-1495/G/87, C/o. Dr.K.T.Paladi, Goudutai Nagar, Kalaburigi - 585102 |  |  | TEL | 040 - 23211660
|  |  | FAX | 040 - 23210198
|  |  | TIN No | 29370771492
|  |  | CST No | 29370771492
|  |  | GSTIN No | 29AACCV2054N1ZY
To: The Executive Engineer,(O&M) GESCOM. GULBARGA RURAL1 Division, |  |  | Invoice No | VPL/GLB/METER SHIFTING/113/19-20
|  |  | Invoice Date | 09.03.2020
|  |  | Cust.DWA No | GESCOM /CEE(O)/SEE (Technical)/AEE (DDUGJY)/Indent-1037/DWA/2019-20/shifting of Meter (Gulabarga).
|  |  | Cust.DWA Date | 10.05.2019
|  |  | L.R No & Date | Attached
Bank Details: Vishwanath Projects Ltd., Bank Name: ICICI Bank, A/CNO:000851000149 Branch: Khairatabad,hyderabad, IFSC CODE: ICIC0000008 |  |  | Transporter | Attached
Customer Code
|  |  | Customer GSTIN No | 29AABCG8895R1ZD
Customer CST No
Customer TIN No
Sl.No | Particulers |  |  |  | Amount Rs.
1 | Separate Annexure Enclosed of the Station Materials |  |  |  | 54255.5
2 | Freight and Insurance
|  | I) Total Amount Before Tax |  |  | 54255.5
|  | a) Add : CGST |  |  | 0
|  | b) Add : SGST |  |  | 0
c) Add : IGST
|  | II) Tax Amount : GST (a+b+c) |  |  | 0
|  | Now Claiming 30% Grand Total Amount |  |  | 16277
Total Amount in words Sixteen thousand two hundred and seventy seven rupees only |  |  | TERMS OF PAYMENT
|  |  | Retention 10% Amount after Completion |  | 5425.55
|  |  | Net Payable Amount |  | 16277
For Vishwanath Projects Ltd.
Authorised Signatory
Certificate:
Certified that the above materials have been supplied by the TTK contractor of M/S Vishwanth Projects Limited.,
As shown as per DWA, the same have been stored at Kalaburagi,Tq and District Kalaburagi .
site and using for shifting of consumers Meters from inside to outside the premises of LT installation by
and replacement of existing electromechanical energy meters by static meters in Gulbarga District under DDUGJY on Total Turnkey basis
Certified that the quantitty of materials furnished in the bill verified with supporting invoices and these materials found as per Gescom specifications.Certified that we have Physically Verified the above materials
| Section Officer |  | Asst Executive Engineer(Ele) |  | Executive Engineer (Ele)
| O&M Section |  | O&M Sub Division |  | O&M Rural Dn.No.1
| Kadaganchi |  | Kadaganchi |  | KALABURAGI.

## Madan hip ere.114
GULBARGA ELECTRICITY SUPPLY COMPANY LIMITED
Name of the Work :shifting of consumers Meters from inside to outside the premises of LT installation and replacement of existing electromechanical energy meters by static meters in Gulbarga District under DDUGJY on Total Turnkey basis
Name of the Contractor: M/s Vishwanath Projects Limited, House No 3-5-874/A, Flat No 401 4th Floor, Hyderguda, Hyderabad (telangana)
LOI No & Date : GESCOM/CEE(O)/SEE(Technical) AEE(DDUGJY)18-19/62017-30 dt 2-02-2019
DWA No & Date : GESCOM/CEE(O)/SEE(Technical)/AEE(DDUGJY)/INDENT-1037/DWA/2019-20/10023-32 dated 10-05-2019 for Supply and erection portion.
2nd bill ERECTION PORTION | [11 empty] | Annexure-I
Invoice No/Bill No:VPL/GLB/MeterShifting/Erection/114/19-20 dt: 09.03.2020 | [11 empty] | WORK ORDER NO : DK-33566 Dt: 16.03.2019
S.No | Item Description | UOM | HSN CODE | Total Qty | Ex-works Price | GST in Rs | Total amount (Including GST) | Previous Bill caimed Qty | Claimed Qty | Cumulative Qty(Including This Bill) | unit ex works price | ex works price (total) | GST (18%) in Rs | GST Amount In Rs. | Total Value
1 | 2 | 3 |  | 4 | 5a | 5b | 5c=5a=5b | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
ERECTION PORTION :
1 | Deep Drawn Metal Meter Box along with suitable screws for fixing to the wall. | Nos. | 85371000 | 70747 | 6595035.34 | 1187134.66 | 7782170 | 181 | 37 | 218 | 93.22 | 3449.14 | 16.78 | 620.86 | 4070
Total | [7 empty] | 10: 3449.14; 12: 620.86; 13: 4070
less 10 % amount payable after completion | [7 empty] | 13: 344.914
NOW Claiming 90% on Ex works price | [7 empty] | 13: 3104.226
100% Taxes | [7 empty] | 13: 620.86
Total amount of Invoice | [7 empty] | 13: 3725.086
Total Amount in words Three thousand seven hundred and twenty five rupees only
CERTIFICATE
Certified that the above materials have been supplied by the M/s Vishwanath Projects limited , as shown as per DWA. The same have been stored at GULBARGA
site and using for shifting of consumers Meters from inside to outside the premises of LT installation In Aland Sub-division , Gulbarga Rual Division Under DDUGJY on Total Turnkey Basis.
Certified that the quantitty of materials furnished in the bill verified and these material found as per Gescom specifications.
Certified that we have physically verified the above materials
| Section Officer | [5 empty] | Asst Executive Engineer(Ele) | 10: Executive Engineer (Ele)
| O&M Section | [5 empty] | O&M Sub Division | 10: O&M Rural Dn.No.1
| Madan Hipparga | [5 empty] | Aland | 10: KALABURAGI.

## Madan hip ere.114(A)
TAX INVOICE
ERECTION BILL
Name of the Work: shifting of consumers Meters from inside to outside the premises of LT installation and replacement of existing electromechanical energy meters by static meters in Gulbarga District under DDUGJY on Total Turnkey basis Name of the Contractor: M/s Vishwanath Projects Limited, House No 3-5-874/A, Flat No 401 4th Floor, Hyderguda, Hyderabad (telangana) LOI No & Date: GESCOM/CEE(O)/SEE(Technical) AEE(DDUGJY)/2018-19/62017-30 dt 2-02-2019 DWA No & Date: GESCOM/CEE(O)/SEE(Technical)/AEE(DDUGJY)/INDENT-1037/DWA/2019-20/10023-32 dated 10-05-2019 for Supply and erection portion
2nd BILL ERECTION PORTION |  |  |  |  | Annexure-I
WORK ORDER NO : DK-33566 Dt: 16.03.2019
INVOICE : VPL/GESCOM/GLB/Meter Shifting/Erection/114/19-20 dt 09-03-2020
Address : Vishwanath Projects Ltd, Hounse No. 1-1495/G/87, C/o. Dr.K.T.Paladi, Goudutai Nagar, Kalaburigi - 585102 |  |  | TEL | 040 - 23211660
|  |  | FAX | 040 - 23210198
|  |  | TIN No | 29370771492
|  |  | CST No | 29370771492
|  |  | GSTIN No | 29AACCV2054N1ZY
To: The Executive Engineer,(O&M) GESCOM. GULBARGA RURAL1 Division, |  |  | Invoice No | VPL/GLB/METER SHIFTING/114/19-20
|  |  | Invoice Date | 09.03.2020
|  |  | Cust.DWA No | GESCOM /CEE(O)/SEE (Technical)/AEE (DDUGJY)/Indent-1037/DWA/2019-20/shifting of Meter (Gulabarga).
|  |  | Cust.DWA Date | 10.05.2019
|  |  | L.R No & Date | Attached
Bank Details: Vishwanath Projects Ltd., Bank Name: ICICI Bank, A/CNO:000851000149 Branch: Khairatabad,hyderabad, IFSC CODE: ICIC0000008 |  |  | Transporter | Attached
Customer Code
|  |  | Customer GSTIN No | 29AABCG8895R1ZD
Customer CST No
Customer TIN No
Sl.No | Particulers |  |  |  | Amount Rs.
1 | Separate Annexure Enclosed of the Station Materials |  |  |  | 3449.14
2 | Freight and Insurance
|  | I) Total Amount Before Tax |  |  | 3449.14
|  | a) Add : CGST |  |  | 310.43
|  | b) Add : SGST |  |  | 310.43
c) Add : IGST
|  | II) Tax Amount : GST (a+b+c) |  |  | 620.86
|  | Now Claiming 90% Ex-works ans Total Gst 100% |  |  | 3725.086
Total Amount in words Three thousand seven hundred and twenty five rupees only |  |  | TERMS OF PAYMENT
|  |  | Retention 10% Amount after Completion |  | 344.914
|  |  | Net Payable Amount |  | 3725.086
For Vishwanath Projects Ltd.
Authorised Signatory
1. W.O .N O & Date : DK-33566 dt :16-03-2019
2. Estimate Cost : Erection Cost : Rs. 4070 /-
3. Name of the Authority : Executive Engineer( Elect), O&M Division-I, GESCOM, Gulbarga.
4.Name of the Agency : M/S Vishwanath Projects Limited, Hyderabad.
5. Date Of Commencement : 10.05.2019 |  |  |  | 6. Date Of Completion : 18.12.2019
7. Date Of Measurment : 08.01.2020 |  |  | 8. MB Book No. |  | Page no
1.DI Date : GESCOM /CEE(O)/SEE(Tech)/EEE(DDUGJY)/19-20/13566-81/dt :28-05-2019
2. BG NO: 2423-BG-22-2019 dt .02-03-2019 to 25/11/2020
Certificate:
Certified that the above materials have been supplied by the TTK contractor of M/S Vishwanth Projects Limited.,
As shown as per DWA, the same have been stored at Kalaburagi,Tq and District Kalaburagi .
site and using for shifting of consumers Meters from inside to outside the premises of LT installation
in Aland Sub-Division, Gulbarga Rural Divisional ,Gulbarga District under DDUGJY on Total Turnkey basis
Certified that the quantitty of materials furnished in the bill verified with supporting invoices and these materials found as per Gescom specifications.Certified that we have Physically Verified the above materials
| Section Officer |  | Asst Executive Engineer(Ele) |  | Executive Engineer (Ele)
| O&M Section |  | O&M Sub Division |  | O&M Rural Dn.No.1
| Madan Hipparga |  | Aland |  | KALABURAGI.

## Madan hip retn.114
GULBARGA ELECTRICITY SUPPLY COMPANY LIMITED
Name of the Work :shifting of consumers Meters from inside to outside the premises of LT installation and replacement of existing electromechanical energy meters by static meters in Gulbarga District under DDUGJY on Total Turnkey basis
Name of the Contractor: M/s Vishwanath Projects Limited, House No 3-5-874/A, Flat No 401 4th Floor, Hyderguda, Hyderabad (telangana)
LOI No & Date : GESCOM/CEE(O)/SEE(Technical) AEE(DDUGJY)18-19/62017-30 dt 2-02-2019
DWA No & Date : GESCOM/CEE(O)/SEE(Technical)/AEE(DDUGJY)/INDENT-1037/DWA/2019-20/10023-32 dated 10-05-2019 for Supply and erection portion.
2nd RETENTION BILL | [9 empty] | Annexure-I
Invoice No/Bill No:VPL/GLB/Meter Shifting/Retn/114/19-20 dt:09.03.2020 | [9 empty] | WORK ORDER NO : DK-33566 Dt: 16.03.2019
S.No | Item Description | UOM | HSN CODE | Total Qty | Ex-works Price | GST in Rs | Total amount (Including GST) | Previous Bill caimed Qty | Claimed Qty | Cumulative Qty(Including This Bill) | unit ex works price | ex works price (total) | GST (18%) in Rs | Total Value
1 | 2 | 3 |  | 4 | 5a | 5b | 5c=5a=5b | 6 | 7 | 8 | 9 | 10 | 11 | 12
SUPPLY PORTION :
1 | Supply of Deep Drawn Metal Box | Nos. | 85371000 | 70747 | 32975176.7 | 5935673.3 | 38910850 | 181 | 37 | 218 | 466.1 | 17245.7 | 0 | 17245.7
Total | [7 empty] | 10: 17245.7; 12: 17245.7
Total Supply Value | [7 empty] | 12: 17246
NOW Claiming 30% on Ex works price | [7 empty] | 12: 5173.8
10% Claiming after completion | [7 empty] | 12: 1724.57
CGST 9% | [7 empty] | 12: 0
SGST 9% | [7 empty] | 12: 0
Total amount of Invoice | [7 empty] | 12: 5173.8
Total Amount in words Five thousand one hundred and seventy four rupees only
CERTIFICATE
Certified that the above materials have been supplied by the M/s Vishwanath Projects limited , as shown as per DWA. The same have been stored at GULBARGA
site and using for shifting of consumers Meters from inside to outside the premises of LT installation In Aland Sub-division , Gulbarga Rual Division Under DDUGJY on Total Turnkey Basis.
Certified that the quantitty of materials furnished in the bill verified and these material found as per Gescom specifications.
Certified that we have physically verified the above materials
| Section Officer |  |  |  |  | Asst Executive Engineer(Ele) |  | 10: Executive Engineer (Ele)
| O&M Section |  |  |  |  | O&M Sub Division |  | 10: O&M Rural Dn.No.1
| Madan Hipparga |  |  |  |  | Aland |  | 10: KALABURAGI.

## Madan hip retn.114(A)
TAX INVOICE
RETENTION BILL
Name of the Work: shifting of consumers Meters from inside to outside the premises of LT installation and replacement of existing electromechanical energy meters by static meters in Gulbarga District under DDUGJY on Total Turnkey basis Name of the Contractor: M/s Vishwanath Projects Limited, House No 3-5-874/A, Flat No 401 4th Floor, Hyderguda, Hyderabad (telangana) LOI No & Date: GESCOM/CEE(O)/SEE(Technical) AEE(DDUGJY)/2018-19/62017-30 dt 2-02-2019 DWA No & Date: GESCOM/CEE(O)/SEE(Technical)/AEE(DDUGJY)/INDENT-1037/DWA/2019-20/10023-32 dated 10-05-2019 for Supply and erection portion
2nd RETENTION BILL |  |  |  |  | Annexue-I
WORK ORDER NO : DK-33566 Dt: 16.03.2019
INVOICE : VPL/GESCOM/GLB/Meter Shifting/Retn Supply/114/19-20 dt 09-03-2020
Address : Vishwanath Projects Ltd, Hounse No. 1-1495/G/87, C/o. Dr.K.T.Paladi, Goudutai Nagar, Kalaburigi - 585102 |  |  | TEL | 040 - 23211660
|  |  | FAX | 040 - 23210198
|  |  | TIN No | 29370771492
|  |  | CST No | 29370771492
|  |  | GSTIN No | 29AACCV2054N1ZY
To: The Executive Engineer,(O&M) GESCOM. GULBARGA RURAL1 Division, |  |  | Invoice No | VPL/GLB/METER SHIFTING/114/19-20
|  |  | Invoice Date | 09.03.2020
|  |  | Cust.DWA No | GESCOM /CEE(O)/SEE (Technical)/AEE (DDUGJY)/Indent-1037/DWA/2019-20/shifting of Meter (Gulabarga).
|  |  | Cust.DWA Date | 10.05.2019
|  |  | L.R No & Date | Attached
Bank Details: Vishwanath Projects Ltd., Bank Name: ICICI Bank, A/CNO:000851000149 Branch: Khairatabad,hyderabad, IFSC CODE: ICIC0000008 |  |  | Transporter | Attached
Customer Code
|  |  | Customer GSTIN No | 29AABCG8895R1ZD
Customer CST No
Customer TIN No
Sl.No | Particulers |  |  |  | Amount Rs.
1 | Separate Annexure Enclosed of the Station Materials |  |  |  | 17245.7
2 | Freight and Insurance
|  | I) Total Amount Before Tax |  |  | 17245.7
|  | a) Add : CGST |  |  | 0
|  | b) Add : SGST |  |  | 0
c) Add : IGST
|  | II) Tax Amount : GST (a+b+c) |  |  | 0
|  | Now Claiming 30% Grand Total Amount |  |  | 5174
Total Amount in words Five thousand one hundred and seventy four rupees only |  |  | TERMS OF PAYMENT
|  |  | Retention 10% Amount after Completion |  | 1724.57
|  |  | Net Payable Amount |  | 5174
For Vishwanath Projects Ltd.
Authorised Signatory
Certificate:
Certified that the above materials have been supplied by the TTK contractor of M/S Vishwanth Projects Limited.,
As shown as per DWA, the same have been stored at Kalaburagi,Tq and District Kalaburagi .
site and using for shifting of consumers Meters from inside to outside the premises of LT installation by
and replacement of existing electromechanical energy meters by static meters in Gulbarga District under DDUGJY on Total Turnkey basis
Certified that the quantitty of materials furnished in the bill verified with supporting invoices and these materials found as per Gescom specifications.Certified that we have Physically Verified the above materials
| Section Officer |  | Asst Executive Engineer(Ele) |  | Executive Engineer (Ele)
| O&M Section |  | O&M Sub Division |  | O&M Rural Dn.No.1
| Madan Hipparga |  | Aland |  | KALABURAGI.

## Khajuri ere.115
GULBARGA ELECTRICITY SUPPLY COMPANY LIMITED
Name of the Work :shifting of consumers Meters from inside to outside the premises of LT installation and replacement of existing electromechanical energy meters by static meters in Gulbarga District under DDUGJY on Total Turnkey basis
Name of the Contractor: M/s Vishwanath Projects Limited, House No 3-5-874/A, Flat No 401 4th Floor, Hyderguda, Hyderabad (telangana)
LOI No & Date : GESCOM/CEE(O)/SEE(Technical) AEE(DDUGJY)18-19/62017-30 dt 2-02-2019
DWA No & Date : GESCOM/CEE(O)/SEE(Technical)/AEE(DDUGJY)/INDENT-1037/DWA/2019-20/10023-32 dated 10-05-2019 for Supply and erection portion.
1st bill ERECTION PORTION | [11 empty] | Annexure-I
Invoice No/Bill No:VPL/GLB/MeterShifting/Erection/115/19-20 dt: 09.03.2020 | [11 empty] | WORK ORDER NO : DK-33564 Dt: 16.03.2019
S.No | Item Description | UOM | HSN CODE | Total Qty | Ex-works Price | GST in Rs | Total amount (Including GST) | Previous Bill caimed Qty | Claimed Qty | Cumulative Qty(Including This Bill) | unit ex works price | ex works price (total) | GST (18%) in Rs | GST Amount In Rs. | Total Value
1 | 2 | 3 |  | 4 | 5a | 5b | 5c=5a=5b | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
ERECTION PORTION :
1 | Deep Drawn Metal Meter Box along with suitable screws for fixing to the wall. | Nos. | 85371000 | 70747 | 6595035.34 | 1187134.66 | 7782170 | 0 | 34 | 34 | 93.22 | 3169.48 | 16.78 | 570.52 | 3740
Total | [7 empty] | 10: 3169.48; 12: 570.52; 13: 3740
less 10 % amount payable after completion | [7 empty] | 13: 316.948
NOW Claiming 90% on Ex works price | [7 empty] | 13: 2852.532
100% Taxes | [7 empty] | 13: 570.52
Total amount of Invoice | [7 empty] | 13: 3423.052
Total Amount in words Three thousand four hundred and twenty three rupees only
CERTIFICATE
Certified that the above materials have been supplied by the M/s Vishwanath Projects limited , as shown as per DWA. The same have been stored at GULBARGA
site and using for shifting of consumers Meters from inside to outside the premises of LT installation In Aland Sub-division , Gulbarga Rual Division Under DDUGJY on Total Turnkey Basis.
Certified that the quantitty of materials furnished in the bill verified and these material found as per Gescom specifications.
Certified that we have physically verified the above materials
| Section Officer | [5 empty] | Asst Executive Engineer(Ele) | 10: Executive Engineer (Ele)
| O&M Section | [5 empty] | O&M Sub Division | 10: O&M Rural Dn.No.1
| Khajuri | [5 empty] | Aland | 10: KALABURAGI.

## khajuri ere.115(A)
TAX INVOICE
ERECTION BILL
Name of the Work: shifting of consumers Meters from inside to outside the premises of LT installation and replacement of existing electromechanical energy meters by static meters in Gulbarga District under DDUGJY on Total Turnkey basis Name of the Contractor: M/s Vishwanath Projects Limited, House No 3-5-874/A, Flat No 401 4th Floor, Hyderguda, Hyderabad (telangana) LOI No & Date: GESCOM/CEE(O)/SEE(Technical) AEE(DDUGJY)/2018-19/62017-30 dt 2-02-2019 DWA No & Date: GESCOM/CEE(O)/SEE(Technical)/AEE(DDUGJY)/INDENT-1037/DWA/2019-20/10023-32 dated 10-05-2019 for Supply and erection portion
1st BILL ERECTION PORTION |  |  |  |  | Annexure-I
WORK ORDER NO : DK-33564 Dt: 16.03.2019
INVOICE : VPL/GESCOM/GLB/Meter Shifting/Erection/115/19-20 dt 09-03-2020
Address : Vishwanath Projects Ltd, Hounse No. 1-1495/G/87, C/o. Dr.K.T.Paladi, Goudutai Nagar, Kalaburigi - 585102 |  |  | TEL | 040 - 23211660
|  |  | FAX | 040 - 23210198
|  |  | TIN No | 29370771492
|  |  | CST No | 29370771492
|  |  | GSTIN No | 29AACCV2054N1ZY
To: The Executive Engineer,(O&M) GESCOM. GULBARGA RURAL1 Division, |  |  | Invoice No | VPL/GLB/METER SHIFTING/115/19-20
|  |  | Invoice Date | 09.03.2020
|  |  | Cust.DWA No | GESCOM /CEE(O)/SEE (Technical)/AEE (DDUGJY)/Indent-1037/DWA/2019-20/shifting of Meter (Gulabarga).
|  |  | Cust.DWA Date | 10.05.2019
|  |  | L.R No & Date | Attached
Bank Details: Vishwanath Projects Ltd., Bank Name: ICICI Bank, A/CNO:000851000149 Branch: Khairatabad,hyderabad, IFSC CODE: ICIC0000008 |  |  | Transporter | Attached
Customer Code
|  |  | Customer GSTIN No | 29AABCG8895R1ZD
Customer CST No
Customer TIN No
Sl.No | Particulers |  |  |  | Amount Rs.
1 | Separate Annexure Enclosed of the Station Materials |  |  |  | 3169.48
2 | Freight and Insurance
|  | I) Total Amount Before Tax |  |  | 3169.48
|  | a) Add : CGST |  |  | 285.26
|  | b) Add : SGST |  |  | 285.26
c) Add : IGST
|  | II) Tax Amount : GST (a+b+c) |  |  | 570.52
|  | Now Claiming 90% Ex-works ans Total Gst 100% |  |  | 3423.052
Total Amount in words Three thousand four hundred and twenty three rupees only |  |  | TERMS OF PAYMENT
|  |  | Retention 10% Amount after Completion |  | 316.948
|  |  | Net Payable Amount |  | 3423.052
For Vishwanath Projects Ltd.
Authorised Signatory
1. W.O .N O & Date : DK-33564 dt :16-03-2019
2. Estimate Cost : Erection Cost : Rs. 3740 /-
3. Name of the Authority : Executive Engineer( Elect), O&M Division-I, GESCOM, Gulbarga.
4.Name of the Agency : M/S Vishwanath Projects Limited, Hyderabad.
5. Date Of Commencement : 10.05.2019 |  |  |  | 6. Date Of Completion : 19.12.2019
7. Date Of Measurment : 18.01.2020 |  |  | 8. MB Book No. |  | Page no
1.DI Date : GESCOM /CEE(O)/SEE(Tech)/EEE(DDUGJY)/19-20/13566-81/dt :28-05-2019
2. BG NO: 2423-BG-22-2019 dt .02-03-2019 to 25/11/2020
Certificate:
Certified that the above materials have been supplied by the TTK contractor of M/S Vishwanth Projects Limited.,
As shown as per DWA, the same have been stored at Kalaburagi,Tq and District Kalaburagi .
site and using for shifting of consumers Meters from inside to outside the premises of LT installation
in Aland Sub-Division, Gulbarga Rural Divisional ,Gulbarga District under DDUGJY on Total Turnkey basis
Certified that the quantitty of materials furnished in the bill verified with supporting invoices and these materials found as per Gescom specifications.Certified that we have Physically Verified the above materials
| Section Officer |  | Asst Executive Engineer(Ele) |  | Executive Engineer (Ele)
| O&M Section |  | O&M Sub Division |  | O&M Rural Dn.No.1
| Khajuri |  | Aland |  | KALABURAGI.

## khajuri retn.115
GULBARGA ELECTRICITY SUPPLY COMPANY LIMITED
Name of the Work :shifting of consumers Meters from inside to outside the premises of LT installation and replacement of existing electromechanical energy meters by static meters in Gulbarga District under DDUGJY on Total Turnkey basis
Name of the Contractor: M/s Vishwanath Projects Limited, House No 3-5-874/A, Flat No 401 4th Floor, Hyderguda, Hyderabad (telangana)
LOI No & Date : GESCOM/CEE(O)/SEE(Technical) AEE(DDUGJY)18-19/62017-30 dt 2-02-2019
DWA No & Date : GESCOM/CEE(O)/SEE(Technical)/AEE(DDUGJY)/INDENT-1037/DWA/2019-20/10023-32 dated 10-05-2019 for Supply and erection portion.
1st RETENTION BILL | [9 empty] | Annexure-I
Invoice No/Bill No:VPL/GLB/Meter Shifting/Retn/115/19-20 dt:09.03.2020 | [9 empty] | WORK ORDER NO : DK-33564 Dt: 16.03.2019
S.No | Item Description | UOM | HSN CODE | Total Qty | Ex-works Price | GST in Rs | Total amount (Including GST) | Previous Bill caimed Qty | Claimed Qty | Cumulative Qty(Including This Bill) | unit ex works price | ex works price (total) | GST (18%) in Rs | Total Value
1 | 2 | 3 |  | 4 | 5a | 5b | 5c=5a=5b | 6 | 7 | 8 | 9 | 10 | 11 | 12
SUPPLY PORTION :
1 | Supply of Deep Drawn Metal Box | Nos. | 85371000 | 70747 | 32975176.7 | 5935673.3 | 38910850 | 0 | 34 | 34 | 466.1 | 15847.4 | 0 | 15847.4
Total | [7 empty] | 10: 15847.4; 12: 15847.4
Total Supply Value | [7 empty] | 12: 15847
NOW Claiming 30% on Ex works price | [7 empty] | 12: 4754.1
10% Claiming after completion | [7 empty] | 12: 1584.74
CGST 9% | [7 empty] | 12: 0
SGST 9% | [7 empty] | 12: 0
Total amount of Invoice | [7 empty] | 12: 4754.1
Total Amount in words Five thousand seven hundred and fifty four rupees only
CERTIFICATE
Certified that the above materials have been supplied by the M/s Vishwanath Projects limited , as shown as per DWA. The same have been stored at GULBARGA
site and using for shifting of consumers Meters from inside to outside the premises of LT installation In Aland Sub-division , Gulbarga Rual Division Under DDUGJY on Total Turnkey Basis.
Certified that the quantitty of materials furnished in the bill verified and these material found as per Gescom specifications.
Certified that we have physically verified the above materials
| Section Officer |  |  |  |  | Asst Executive Engineer(Ele) |  | 10: Executive Engineer (Ele)
| O&M Section |  |  |  |  | O&M Sub Division |  | 10: O&M Rural Dn.No.1
| Khajuri |  |  |  |  | Aland |  | 10: KALABURAGI.

## khajuri retn.115(A)
TAX INVOICE
RETENTION BILL
Name of the Work: shifting of consumers Meters from inside to outside the premises of LT installation and replacement of existing electromechanical energy meters by static meters in Gulbarga District under DDUGJY on Total Turnkey basis Name of the Contractor: M/s Vishwanath Projects Limited, House No 3-5-874/A, Flat No 401 4th Floor, Hyderguda, Hyderabad (telangana) LOI No & Date: GESCOM/CEE(O)/SEE(Technical) AEE(DDUGJY)/2018-19/62017-30 dt 2-02-2019 DWA No & Date: GESCOM/CEE(O)/SEE(Technical)/AEE(DDUGJY)/INDENT-1037/DWA/2019-20/10023-32 dated 10-05-2019 for Supply and erection portion
1st RETENTION BILL |  |  |  |  | Annexue-I
WORK ORDER NO : DK-33564 Dt: 16.03.2019
INVOICE : VPL/GESCOM/GLB/Meter Shifting/Retn Supply/115/19-20 dt 09-03-2020
Address : Vishwanath Projects Ltd, Hounse No. 1-1495/G/87, C/o. Dr.K.T.Paladi, Goudutai Nagar, Kalaburigi - 585102 |  |  | TEL | 040 - 23211660
|  |  | FAX | 040 - 23210198
|  |  | TIN No | 29370771492
|  |  | CST No | 29370771492
|  |  | GSTIN No | 29AACCV2054N1ZY
To: The Executive Engineer,(O&M) GESCOM. GULBARGA RURAL1 Division, |  |  | Invoice No | VPL/GLB/METER SHIFTING/115/19-20
|  |  | Invoice Date | 09.03.2020
|  |  | Cust.DWA No | GESCOM /CEE(O)/SEE (Technical)/AEE (DDUGJY)/Indent-1037/DWA/2019-20/shifting of Meter (Gulabarga).
|  |  | Cust.DWA Date | 10.05.2019
|  |  | L.R No & Date | Attached
Bank Details: Vishwanath Projects Ltd., Bank Name: ICICI Bank, A/CNO:000851000149 Branch: Khairatabad,hyderabad, IFSC CODE: ICIC0000008 |  |  | Transporter | Attached
Customer Code
|  |  | Customer GSTIN No | 29AABCG8895R1ZD
Customer CST No
Customer TIN No
Sl.No | Particulers |  |  |  | Amount Rs.
1 | Separate Annexure Enclosed of the Station Materials |  |  |  | 15847.4
2 | Freight and Insurance
|  | I) Total Amount Before Tax |  |  | 15847.4
|  | a) Add : CGST |  |  | 0
|  | b) Add : SGST |  |  | 0
c) Add : IGST
|  | II) Tax Amount : GST (a+b+c) |  |  | 0
|  | Now Claiming 30% Grand Total Amount |  |  | 4754
Total Amount in words Five thousand seven hundred and fifty four rupees only |  |  | TERMS OF PAYMENT
|  |  | Retention 10% Amount after Completion |  | 1584.74
|  |  | Net Payable Amount |  | 4754
For Vishwanath Projects Ltd.
Authorised Signatory
Certificate:
Certified that the above materials have been supplied by the TTK contractor of M/S Vishwanth Projects Limited.,
As shown as per DWA, the same have been stored at Kalaburagi,Tq and District Kalaburagi .
site and using for shifting of consumers Meters from inside to outside the premises of LT installation by
and replacement of existing electromechanical energy meters by static meters in Gulbarga District under DDUGJY on Total Turnkey basis
Certified that the quantitty of materials furnished in the bill verified with supporting invoices and these materials found as per Gescom specifications.Certified that we have Physically Verified the above materials
| Section Officer |  | Asst Executive Engineer(Ele) |  | Executive Engineer (Ele)
| O&M Section |  | O&M Sub Division |  | O&M Rural Dn.No.1
| Khajuri |  | Aland |  | KALABURAGI.

## Nimbarga ere.116
GULBARGA ELECTRICITY SUPPLY COMPANY LIMITED
Name of the Work :shifting of consumers Meters from inside to outside the premises of LT installation and replacement of existing electromechanical energy meters by static meters in Gulbarga District under DDUGJY on Total Turnkey basis
Name of the Contractor: M/s Vishwanath Projects Limited, House No 3-5-874/A, Flat No 401 4th Floor, Hyderguda, Hyderabad (telangana)
LOI No & Date : GESCOM/CEE(O)/SEE(Technical) AEE(DDUGJY)18-19/62017-30 dt 2-02-2019
DWA No & Date : GESCOM/CEE(O)/SEE(Technical)/AEE(DDUGJY)/INDENT-1037/DWA/2019-20/10023-32 dated 10-05-2019 for Supply and erection portion.
2nd bill ERECTION PORTION | [11 empty] | Annexure-I
Invoice No/Bill No:VPL/GLB/MeterShifting/Erection/116/19-20 dt: 09.03.2020 | [11 empty] | WORK ORDER NO : DK-33584 Dt: 16.03.2019
S.No | Item Description | UOM | HSN CODE | Total Qty | Ex-works Price | GST in Rs | Total amount (Including GST) | Previous Bill caimed Qty | Claimed Qty | Cumulative Qty(Including This Bill) | unit ex works price | ex works price (total) | GST (18%) in Rs | GST Amount In Rs. | Total Value
1 | 2 | 3 |  | 4 | 5a | 5b | 5c=5a=5b | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
ERECTION PORTION :
1 | Deep Drawn Metal Meter Box along with suitable screws for fixing to the wall. | Nos. | 85371000 | 70747 | 6595035.34 | 1187134.66 | 7782170 | 792 | 282 | 1074 | 93.22 | 26288.04 | 16.78 | 4731.96 | 31020
Total | [7 empty] | 10: 26288.04; 12: 4731.96; 13: 31020
less 10 % amount payable after completion | [7 empty] | 13: 2628.804
NOW Claiming 90% on Ex works price | [7 empty] | 13: 23659.236
100% Taxes | [7 empty] | 13: 4731.96
Total amount of Invoice | [7 empty] | 13: 28391.196
Total Amount in words Twenty Eight thousand three hundred and ninety one rupees only
CERTIFICATE
Certified that the above materials have been supplied by the M/s Vishwanath Projects limited , as shown as per DWA. The same have been stored at GULBARGA
site and using for shifting of consumers Meters from inside to outside the premises of LT installation In Kadaganchi Sub-division , Gulbarga Rual Division Under DDUGJY on Total Turnkey Basis.
Certified that the quantitty of materials furnished in the bill verified and these material found as per Gescom specifications.
Certified that we have physically verified the above materials
| Section Officer | [5 empty] | Asst Executive Engineer(Ele) | 10: Executive Engineer (Ele)
| O&M Section | [5 empty] | O&M Sub Division | 10: O&M Rural Division-1
| Nimbarga | [5 empty] | Kadaganchi | 10: KALABURAGI.

## Nimbarga ere.116(A)
TAX INVOICE
ERECTION BILL
Name of the Work: shifting of consumers Meters from inside to outside the premises of LT installation and replacement of existing electromechanical energy meters by static meters in Gulbarga District under DDUGJY on Total Turnkey basis Name of the Contractor: M/s Vishwanath Projects Limited, House No 3-5-874/A, Flat No 401 4th Floor, Hyderguda, Hyderabad (telangana) LOI No & Date: GESCOM/CEE(O)/SEE(Technical) AEE(DDUGJY)/2018-19/62017-30 dt 2-02-2019 DWA No & Date: GESCOM/CEE(O)/SEE(Technical)/AEE(DDUGJY)/INDENT-1037/DWA/2019-20/10023-32 dated 10-05-2019 for Supply and erection portion
2nd BILL ERECTION PORTION |  |  |  |  | Annexure-I
WORK ORDER NO : DK-33584 Dt: 16.03.2019
INVOICE : VPL/GESCOM/GLB/Meter Shifting/Erection/116/19-20 dt 09-03-2020
Address : Vishwanath Projects Ltd, Hounse No. 1-1495/G/87, C/o. Dr.K.T.Paladi, Goudutai Nagar, Kalaburigi - 585102 |  |  | TEL | 040 - 23211660
|  |  | FAX | 040 - 23210198
|  |  | TIN No | 29370771492
|  |  | CST No | 29370771492
|  |  | GSTIN No | 29AACCV2054N1ZY
To: The Executive Engineer,(O&M) GESCOM. GULBARGA RURAL1 Division, |  |  | Invoice No | VPL/GLB/METER SHIFTING/116/19-20
|  |  | Invoice Date | 09.03.2020
|  |  | Cust.DWA No | GESCOM /CEE(O)/SEE (Technical)/AEE (DDUGJY)/Indent-1037/DWA/2019-20/shifting of Meter (Gulabarga).
|  |  | Cust.DWA Date | 10.05.2019
|  |  | L.R No & Date | Attached
Bank Details: Vishwanath Projects Ltd., Bank Name: ICICI Bank, A/CNO:000851000149 Branch: Khairatabad,hyderabad, IFSC CODE: ICIC0000008 |  |  | Transporter | Attached
Customer Code
|  |  | Customer GSTIN No | 29AABCG8895R1ZD
Customer CST No
Customer TIN No
Sl.No | Particulers |  |  |  | Amount Rs.
1 | Separate Annexure Enclosed of the Station Materials |  |  |  | 26288.04
2 | Freight and Insurance
|  | I) Total Amount Before Tax |  |  | 26288.04
|  | a) Add : CGST |  |  | 2365.98
|  | b) Add : SGST |  |  | 2365.98
c) Add : IGST
|  | II) Tax Amount : GST (a+b+c) |  |  | 4731.96
|  | Now Claiming 90% Ex-works ans Total Gst 100% |  |  | 28391.196
Total Amount in words Twenty Eight thousand three hundred and ninety one rupees only |  |  | TERMS OF PAYMENT
|  |  | Retention 10% Amount after Completion |  | 2628.804
|  |  | Net Payable Amount |  | 28391.196
For Vishwanath Projects Ltd.
Authorised Signatory
1. W.O .N O & Date : DK-33584 dt :16-03-2019
2. Estimate Cost : Erection Cost : Rs. 31020/-
3. Name of the Authority : Executive Engineer( Elect), O&M Division-I, GESCOM, Gulbarga.
4.Name of the Agency : M/S Vishwanath Projects Limited, Hyderabad.
5. Date Of Commencement : 10.05.2019 |  |  |  | 6. Date Of Completion : 20.12.2019
7. Date Of Measurment : 25.01.2020 |  |  | 8. MB Book No. |  | Page no
1.DI Date : GESCOM /CEE(O)/SEE(Tech)/EEE(DDUGJY)/19-20/13566-81/dt :28-05-2019
2. BG NO: 2423-BG-22-2019 dt .02-03-2019 to 25/11/2020
Certificate:
Certified that the above materials have been supplied by the TTK contractor of M/S Vishwanth Projects Limited.,
As shown as per DWA, the same have been stored at Kalaburagi,Tq and District Kalaburagi .
site and using for shifting of consumers Meters from inside to outside the premises of LT installation
in Kadaganchi Sub-Division, Gulbarga Rural Divisional ,Gulbarga District under DDUGJY on Total Turnkey basis
Certified that the quantitty of materials furnished in the bill verified with supporting invoices and these materials found as per Gescom specifications.Certified that we have Physically Verified the above materials
| Section Officer |  | Asst Executive Engineer(Ele) |  | Executive Engineer (Ele)
| O&M Section |  | O&M Sub Division |  | O&M Rural Division-1
| Nimbarga |  | Kadaganchi |  | KALABURAGI.

## Nimbarga retn.116
GULBARGA ELECTRICITY SUPPLY COMPANY LIMITED
Name of the Work :shifting of consumers Meters from inside to outside the premises of LT installation and replacement of existing electromechanical energy meters by static meters in Gulbarga District under DDUGJY on Total Turnkey basis
Name of the Contractor: M/s Vishwanath Projects Limited, House No 3-5-874/A, Flat No 401 4th Floor, Hyderguda, Hyderabad (telangana)
LOI No & Date : GESCOM/CEE(O)/SEE(Technical) AEE(DDUGJY)18-19/62017-30 dt 2-02-2019
DWA No & Date : GESCOM/CEE(O)/SEE(Technical)/AEE(DDUGJY)/INDENT-1037/DWA/2019-20/10023-32 dated 10-05-2019 for Supply and erection portion.
2nd RETENTION BILL | [9 empty] | Annexure-I
Invoice No/Bill No:VPL/GLB/Meter Shifting/Retn/116/19-20 dt:09.03.2020 | [9 empty] | WORK ORDER NO : DK-33584 Dt: 16.03.2019
S.No | Item Description | UOM | HSN CODE | Total Qty | Ex-works Price | GST in Rs | Total amount (Including GST) | Previous Bill caimed Qty | Claimed Qty | Cumulative Qty(Including This Bill) | unit ex works price | ex works price (total) | GST (18%) in Rs | Total Value
1 | 2 | 3 |  | 4 | 5a | 5b | 5c=5a=5b | 6 | 7 | 8 | 9 | 10 | 11 | 12
SUPPLY PORTION :
1 | Supply of Deep Drawn Metal Box | Nos. | 85371000 | 70747 | 32975176.7 | 5935673.3 | 38910850 | 792 | 282 | 1074 | 466.1 | 131440.2 | 0 | 131440.2
Total | [7 empty] | 10: 131440.2; 12: 131440.2
Total Supply Value | [7 empty] | 12: 131440
NOW Claiming 30% on Ex works price | [7 empty] | 12: 39432
10% Claiming after completion | [7 empty] | 12: 13144.02
CGST 9% | [7 empty] | 12: 0
SGST 9% | [7 empty] | 12: 0
Total amount of Invoice | [7 empty] | 12: 39432
Total Amount in words Thirty nine thousand four hundred and thirty two rupees only
CERTIFICATE
Certified that the above materials have been supplied by the M/s Vishwanath Projects limited , as shown as per DWA. The same have been stored at GULBARGA
site and using for shifting of consumers Meters from inside to outside the premises of LT installation In Kadaganchi Sub-division , Gulbarga Rual Division Under DDUGJY on Total Turnkey Basis.
Certified that the quantitty of materials furnished in the bill verified and these material found as per Gescom specifications.
Certified that we have physically verified the above materials
| Section Officer |  |  |  |  | Asst Executive Engineer(Ele) |  | 10: Executive Engineer (Ele)
| O&M Section |  |  |  |  | O&M Sub Division |  | 10: O&M Rural Division-1
| Nimbarga |  |  |  |  | Kadaganchi |  | 10: KALABURAGI.

## Nimbarga retn.116(A)
TAX INVOICE
RETENTION BILL
Name of the Work: shifting of consumers Meters from inside to outside the premises of LT installation and replacement of existing electromechanical energy meters by static meters in Gulbarga District under DDUGJY on Total Turnkey basis Name of the Contractor: M/s Vishwanath Projects Limited, House No 3-5-874/A, Flat No 401 4th Floor, Hyderguda, Hyderabad (telangana) LOI No & Date: GESCOM/CEE(O)/SEE(Technical) AEE(DDUGJY)/2018-19/62017-30 dt 2-02-2019 DWA No & Date: GESCOM/CEE(O)/SEE(Technical)/AEE(DDUGJY)/INDENT-1037/DWA/2019-20/10023-32 dated 10-05-2019 for Supply and erection portion
2nd RETENTION BILL |  |  |  |  | Annexue-I
WORK ORDER NO : DK-33584 Dt: 16.03.2019
INVOICE : VPL/GESCOM/GLB/Meter Shifting/Retn Supply/116/19-20 dt 09-03-2020
Address : Vishwanath Projects Ltd, Hounse No. 1-1495/G/87, C/o. Dr.K.T.Paladi, Goudutai Nagar, Kalaburigi - 585102 |  |  | TEL | 040 - 23211660
|  |  | FAX | 040 - 23210198
|  |  | TIN No | 29370771492
|  |  | CST No | 29370771492
|  |  | GSTIN No | 29AACCV2054N1ZY
To: The Executive Engineer,(O&M) GESCOM. GULBARGA RURAL1 Division, |  |  | Invoice No | VPL/GLB/METER SHIFTING/116/19-20
|  |  | Invoice Date | 09.03.2020
|  |  | Cust.DWA No | GESCOM /CEE(O)/SEE (Technical)/AEE (DDUGJY)/Indent-1037/DWA/2019-20/shifting of Meter (Gulabarga).
|  |  | Cust.DWA Date | 10.05.2019
|  |  | L.R No & Date | Attached
Bank Details: Vishwanath Projects Ltd., Bank Name: ICICI Bank, A/CNO:000851000149 Branch: Khairatabad,hyderabad, IFSC CODE: ICIC0000008 |  |  | Transporter | Attached
Customer Code
|  |  | Customer GSTIN No | 29AABCG8895R1ZD
Customer CST No
Customer TIN No
Sl.No | Particulers |  |  |  | Amount Rs.
1 | Separate Annexure Enclosed of the Station Materials |  |  |  | 131440.2
2 | Freight and Insurance
|  | I) Total Amount Before Tax |  |  | 131440.2
|  | a) Add : CGST |  |  | 0
|  | b) Add : SGST |  |  | 0
c) Add : IGST
|  | II) Tax Amount : GST (a+b+c) |  |  | 0
|  | Now Claiming 30% Grand Total Amount |  |  | 39432
Total Amount in words Thirty nine thousand four hundred and thirty two rupees only |  |  | TERMS OF PAYMENT
|  |  | Retention 10% Amount after Completion |  | 13144.02
|  |  | Net Payable Amount |  | 39432
For Vishwanath Projects Ltd.
Authorised Signatory
Certificate:
Certified that the above materials have been supplied by the TTK contractor of M/S Vishwanth Projects Limited.,
As shown as per DWA, the same have been stored at Kalaburagi,Tq and District Kalaburagi .
site and using for shifting of consumers Meters from inside to outside the premises of LT installation by
and replacement of existing electromechanical energy meters by static meters in Gulbarga District under DDUGJY on Total Turnkey basis
Certified that the quantitty of materials furnished in the bill verified with supporting invoices and these materials found as per Gescom specifications.Certified that we have Physically Verified the above materials
| Section Officer |  | Asst Executive Engineer(Ele) |  | Executive Engineer (Ele)
| O&M Section |  | O&M Sub Division |  | O&M Rural Division-1
| Nimbarga |  | Kadaganchi |  | KALABURAGI.